## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF CHOPA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18937 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at EKTARPUR (2Nos.), BELUN (2Nos.), CHOPA (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) |  | ORD/000577/2023-2024 | 3235/HUG | 06/11/2023 | 05/01/2024 | EVERGREEN TRADERS | 59.68 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF CHOPA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18937 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF CHOPA PIPED W/S SCHEME Block- Dhaniakhali District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/001210/2023-2024 | 4488/ED | 23/11/2023 | 21/02/2024 | H.K.DAS & CO. | 21.88 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF CHOPA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18937 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at EKTARPUR (2Nos.), BELUN (2Nos.), CHOPA (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000612/2023-2024 | 3358/HUG | 21/11/2023 | 05/01/2024 | ACME CONSTRUCTION | 87.88 | 0 | 0 | 60
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF CHOPA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18937 | Augmentation | Laying / Repairing Pipeline in damaged portion and other allied works for Chopa & Dighir Piped Water Supply Scheme under Dhaniakhali Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000731/2023-2024 | 23/CH | 05/01/2024 | 20/01/2024 | BOSE ENTERPRISE (RATUL BOSE) | 1.58 | 1.5 | 94.52 | 100
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF CHOPA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18937 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in GURAP-I GP of DHANIAKHALI Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000928/2023-2024 | 248/CH | 12/03/2024 | 11/04/2024 | SAKALER SATHI SWAMBHAR GOSTHI | 4.98 | 0 | 0 | 65
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF CHOPA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18937 | Augmentation | Laying of HDPE pipeline and distribution at the left out portions of Chopa PWSS under Dhaniakhali Block of Chinsurah Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000054/2024-2025 | 2345/HUG | 19/06/2024 | 15/04/2025 | BOSE ENTERPRISE (RATUL BOSE) | 53.11 | 17.58 | 33.09 | 50
7 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF CHOPA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18937 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at CHOPA (1 No.), HARAL (2Nos.), DWARBASINI (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000614/2023-2024 | 3359/HUG | 21/11/2023 | 12/08/2025 | G. T. AGRO CENTRE | 86.34 | 0.56 | 0.65 | 35
Total | [13 empty] | 315.46 | 19.63 | 6.22