## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF HARAL PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18938 | Augmentation | Quotation for new service connection for source Augmentation of HARAL Water Supply Scheme, Zone-III, TW NO- I in the district Hooghly under Electrical Division, PHE Dte. (SM/18938), Reference Id- 503705756, Application no- 5004321019 |  |  | BILL/01632/2024-2025 | 374 | 12/08/2024 | 12/08/2024 | WBSEDCL | 23.02 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF HARAL PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18938 | Augmentation | Quotation for new service connection for source Augmentation of HARAL Water Supply Scheme, Zone-III, TW NO- II in the district Hooghly under Electrical Division, PHE Dte. (SM/18938), Reference Id- 503697548, Application no- 5004304981 |  |  | BILL/01373/2024-2025 | 337 | 30/07/2024 | 30/07/2024 | WBSEDCL | 3.93 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF HARAL PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18938 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at CHOPA (1 No.), HARAL (2Nos.), DWARBASINI (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000578/2023-2024 | 3236/HUG | 06/11/2023 | 01/11/2025 | DAS ENTERPRISE | 59.77 | 0 | 0 | 60
4 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF HARAL PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18938 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF HARAL PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/001211/2023-2024 | 4489/ED | 23/11/2023 | 01/04/2025 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 21.49 | 0 | 0 | 80
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF HARAL PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18938 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Haral Z-II PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) |  | ORD/001922/2024-2025 | 272/CH | 20/02/2025 | 02/03/2025 | M/S SHIVAM UDYOG | 3.18 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF HARAL PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18938 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at H/W Site of Haral Z-I PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) |  | ORD/001861/2024-2025 | 241/CH | 19/02/2025 | 01/03/2025 | M/S SHIVAM UDYOG | 4.84 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF HARAL PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18938 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Haral Z-I PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) |  | ORD/001883/2024-2025 | 245/CH | 19/02/2025 | 01/03/2025 | M/S SHIVAM UDYOG | 2.62 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF HARAL PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18938 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at H/W Site (PH-I) Haral Z-II PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) |  | ORD/001913/2024-2025 | 264/CH | 20/02/2025 | 02/03/2025 | M/S SHIVAM UDYOG | 4.49 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF HARAL PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18938 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at CHOPA (1 No.), HARAL (2Nos.), DWARBASINI (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000614/2023-2024 | 3359/HUG | 21/11/2023 | 12/08/2025 | G. T. AGRO CENTRE | 86.34 | 0 | 0 | 35
Total | [13 empty] | 209.7 | 0 | 0