## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DWARBASINI PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18939 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF DWARBASINI PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/001212/2023-2024 | 4490/ED | 23/11/2023 | 31/08/2025 | M/S S.R. ENTERPRISE | 21.81 | 0 | 0 | 90
2 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DWARBASINI PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18939 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at CHOPA (1 No.), HARAL (2Nos.), DWARBASINI (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000578/2023-2024 | 3236/HUG | 06/11/2023 | 01/05/2026 | DAS ENTERPRISE | 59.77 | 0 | 0 | 60
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DWARBASINI PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18939 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at CHOPA (1 No.), HARAL (2Nos.), DWARBASINI (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000614/2023-2024 | 3359/HUG | 21/11/2023 | 12/08/2025 | G. T. AGRO CENTRE | 86.34 | 0 | 0 | 35
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DWARBASINI PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18939 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Darbasini PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) |  | ORD/001881/2024-2025 | 244/CH | 19/02/2025 | 01/03/2025 | SUNITI MAIRA | 2.72 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DWARBASINI PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18939 | Augmentation | Repairing & Renovation of boundary wall and Land development at H/W Site of Dwarbasini PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) |  | ORD/001910/2024-2025 | 261/CH | 20/02/2025 | 02/03/2025 | BASU & SONS | 4.75 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DWARBASINI PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18939 | Augmentation | Repairing & Renovation of Switch room and Store Room at H/W Site Dwarbasini PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) |  | ORD/001911/2024-2025 | 262/CH | 20/02/2025 | 02/03/2025 | BASU & SONS | 2.85 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DWARBASINI PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18939 | Augmentation | Quotation for new service connection for source Augmentation of DWARBASINI Water Supply Scheme, TW NO-IV in the district Hooghly under Electrical Division, PHE Dte. ( SM/18939), Reference Id- 503873029 Application no- 5004581365 |  |  | BILL/03121/2024-2025 | 712 | 17/03/2025 | 17/03/2025 | WBSEDCL | 3.69 | 0 | 0 | 0
8 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DWARBASINI PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18939 | Augmentation | Quotation for new service connection for source Augmentation of DWARBASINI Water Supply Scheme, TW NO-III in the district Hooghly under Electrical Division, PHEDte. ( SM/18939), Reference Id- 503873481 Application no- 5004581303 |  |  | BILL/03120/2024-2025 | 711 | 17/03/2025 | 17/03/2025 | WBSEDCL | 5.92 | 0 | 0 | 0
Total | [13 empty] | 187.85 | 0 | 0