## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF AYMANABABPUR PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18941 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF AYMANABABPUR PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001259/2023-2024 | 4505/ED | 23/11/2023 | 21/02/2024 | A.G. ENTERPRISE | 21.49 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF AYMANABABPUR PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18941 | Augmentation | Quotation for new service connection for source Augmentation of AYMA NABABPUR Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. ( SM/18941), Reference Id- 503802584 Application no- 5004479744 |  |  | BILL/02530/2024-2025 | 603 | 05/12/2024 | 05/12/2024 | WBSEDCL | 4.01 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF AYMANABABPUR PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18941 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at AYMA NABABPUR (2Nos.), DUMURDAHA (1No.), AKNA (1 No.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000609/2023-2024 | 3356/HUG | 21/11/2023 | 05/11/2025 | AYUSH ENTERPRISE | 58.97 | 0 | 0 | 80
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF AYMANABABPUR PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18941 | Augmentation | Construction of Store room for temporary Chlorine and maintenance material storage For Pandua Block under Chinsurah Sub-Division under Hooghly Division, PHE Dte.under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001036/2023-2024 | 286/CH | 15/03/2024 | 22/03/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0 | 0 | 30
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF AYMANABABPUR PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18941 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at H/W Site of Ayma nababpur PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) |  | ORD/001856/2024-2025 | 235/CH | 19/02/2025 | 01/03/2025 | YOUNG ENGINEERS CO OPERATIVE SOCIETY LTD. | 4.49 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF AYMANABABPUR PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18941 | Augmentation | Repairing & Renovation of Switch room at PH-II of Ayma nababpur PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) |  | ORD/001857/2024-2025 | 236/CH | 19/02/2025 | 01/03/2025 | AYUSH ENTERPRISE | 1.36 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF AYMANABABPUR PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18941 | Augmentation | Laying CI/DI pipes and specials for connection of proposed TW with existing rising main pipeline for Source AUGMENTATION Of Aymanababpur Piped Water Supply Scheme underPandua Block, District:- Hooghly | Assistant Engineer (Civil) |  | ORD/002143/2024-2025 | 357/CH | 28/02/2025 | 07/03/2025 | M/S KAMALA ENTERPRISE | 1 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF AYMANABABPUR PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18941 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at AYMA NABABPUR (2Nos.), DUMURDAHA (1No.), AKNA (1 No.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill),Pandua Block Junior Engineer (Civill) | ORD/000620/2023-2024 | 3386/HUG | 22/11/2023 | 30/12/2024 | OSMAN SEKH | 87.81 | 17.08 | 19.46 | 50
Total | [13 empty] | 180.08 | 17.08 | 9.49