## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18942 | Augmentation | Inter connection work of Rising main from newly bored Tube Well to existing Distribution Main of Dumurdaha Zone-I W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000689/2023-2024 | 1111/CH | 15/12/2023 | 22/12/2023 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.89 | 93.63 | 100
2 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18942 | Augmentation | Laying HDPE Pipeline From existing existing Distribution System for providing FHTC of Dumurdaha Zone-I W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000690/2023-2024 | 1112/CH | 15/12/2023 | 25/12/2023 | MAA BUNAMATA ENTERPRISE | 0.94 | 0.94 | 100 | 100
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18942 | Augmentation | Carriage for Chlorine From Polba Store to different Pump Houses at Pandua & Balagarh Block under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000691/2023-2024 | 1113/CH | 15/12/2023 | 22/12/2023 | MAA BUNAMATA ENTERPRISE | 0.53 | 0.53 | 100 | 100
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18942 | Augmentation | Laying HDPE Pipeline From existing existing Distribution System for providing FHTC of Dumurdaha Zone-I W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000734/2023-2024 | 26/CH | 05/01/2024 | 20/01/2024 | MAA BUNAMATA ENTERPRISE | 1.93 | 1.93 | 100 | 60
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18942 | Augmentation | Providing FHTC at the left out portions of Nayasarai of Dumurdaha Piped Water Supply Scheme under Balagarh Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001033/2023-2024 | 276/CH | 14/03/2024 | 21/03/2024 | MAA BUNAMATA ENTERPRISE | 0.98 | 0.97 | 99.01 | 80
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18942 | Augmentation | Providing FHTC at the left out portions of Ramnagar of Dumurdaha Piped Water Supply Scheme under Balagarh Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001032/2023-2024 | 275/CH | 14/03/2024 | 21/03/2024 | MAA BUNAMATA ENTERPRISE | 0.98 | 0.97 | 99.01 | 80
7 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18942 | Augmentation | Laying HDPE Pipeline From existing Distribution System for providing FHTC of Dumurdaha Zone-I W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000033/2024-2025 | 535/CH | 14/06/2024 | 21/06/2024 | MAA BUNAMATA ENTERPRISE | 4.83 | 4.82 | 99.86 | 80
8 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18942 | Augmentation | Laying HDPE Pipeline From existing existing Distribution System for providing FHTC of Dumurdaha Zone-I W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000042/2024-2025 | 544/CH | 18/06/2024 | 25/06/2024 | MAA BUNAMATA ENTERPRISE | 4.43 | 4.43 | 99.97 | 80
9 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18942 | Augmentation | Quotation for new service connection for source Augmentation of DUMURDHA Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. (SM/18942), Reference Id- 503718763 Application no- 5004350181 |  |  | BILL/01798/2024-2025 | 425 | 01/10/2024 | 01/10/2024 | WBSEDCL | 8.83 | 0 | 0 | 0
10 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18942 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/001261/2023-2024 | 4506/ED | 23/11/2023 | 01/04/2025 | INDTECH ASSOCIATES. | 10.76 | 0 | 0 | 80
11 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18942 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at AYMA NABABPUR (2Nos.), DUMURDAHA (1No.), AKNA (1 No.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000609/2023-2024 | 3356/HUG | 21/11/2023 | 05/11/2025 | AYUSH ENTERPRISE | 58.97 | 0 | 0 | 80
12 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18942 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at AYMA NABABPUR (2Nos.), DUMURDAHA (1No.), AKNA (1 No.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill),Pandua Block Junior Engineer (Civill) | ORD/000620/2023-2024 | 3386/HUG | 22/11/2023 | 30/12/2024 | OSMAN SEKH | 87.81 | 16.12 | 18.36 | 50
Total | [13 empty] | 181.95 | 31.61 | 17.37