## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18942 | Augmentation | Inter connection work of Rising main from newly bored Tube Well to existing Distribution Main of Dumurdaha Zone-I W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000689/2023-2024 | 1111/CH | 15/12/2023 | 22/12/2023 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.89 | 93.63 | 100
2 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18942 | Augmentation | Laying HDPE Pipeline From existing existing Distribution System for providing FHTC of Dumurdaha Zone-I W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000690/2023-2024 | 1112/CH | 15/12/2023 | 25/12/2023 | MAA BUNAMATA ENTERPRISE | 0.94 | 0.94 | 100 | 100
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18942 | Augmentation | Carriage for Chlorine From Polba Store to different Pump Houses at Pandua & Balagarh Block under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000691/2023-2024 | 1113/CH | 15/12/2023 | 22/12/2023 | MAA BUNAMATA ENTERPRISE | 0.53 | 0.53 | 100 | 100
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18942 | Augmentation | Laying HDPE Pipeline From existing existing Distribution System for providing FHTC of Dumurdaha Zone-I W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000734/2023-2024 | 26/CH | 05/01/2024 | 20/01/2024 | MAA BUNAMATA ENTERPRISE | 1.93 | 1.93 | 100 | 60
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18942 | Augmentation | Providing FHTC at the left out portions of Nayasarai of Dumurdaha Piped Water Supply Scheme under Balagarh Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001033/2023-2024 | 276/CH | 14/03/2024 | 21/03/2024 | MAA BUNAMATA ENTERPRISE | 0.98 | 0.97 | 99.01 | 80
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18942 | Augmentation | Providing FHTC at the left out portions of Ramnagar of Dumurdaha Piped Water Supply Scheme under Balagarh Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001032/2023-2024 | 275/CH | 14/03/2024 | 21/03/2024 | MAA BUNAMATA ENTERPRISE | 0.98 | 0.97 | 99.01 | 80
7 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18942 | Augmentation | Laying HDPE Pipeline From existing Distribution System for providing FHTC of Dumurdaha Zone-I W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000033/2024-2025 | 535/CH | 14/06/2024 | 21/06/2024 | MAA BUNAMATA ENTERPRISE | 4.83 | 4.82 | 99.86 | 80
8 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18942 | Augmentation | Laying HDPE Pipeline From existing existing Distribution System for providing FHTC of Dumurdaha Zone-I W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000042/2024-2025 | 544/CH | 18/06/2024 | 25/06/2024 | MAA BUNAMATA ENTERPRISE | 4.43 | 4.43 | 99.97 | 80
9 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18942 | Augmentation | Quotation for new service connection for source Augmentation of DUMURDHA Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. (SM/18942), Reference Id- 503718763 Application no- 5004350181 |  |  | BILL/01798/2024-2025 | 425 | 01/10/2024 | 01/10/2024 | WBSEDCL | 8.83 | 0 | 0 | 0
10 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18942 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/001261/2023-2024 | 4506/ED | 23/11/2023 | 01/04/2025 | INDTECH ASSOCIATES. | 10.76 | 0 | 0 | 80
11 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18942 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at AYMA NABABPUR (2Nos.), DUMURDAHA (1No.), AKNA (1 No.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000609/2023-2024 | 3356/HUG | 21/11/2023 | 05/11/2025 | AYUSH ENTERPRISE | 58.97 | 0 | 0 | 80
Total | [13 empty] | 94.14 | 15.5 | 16.46