## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF AKNA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/18943 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF AKNA PIPED W/S SCHEME Block- Polba-Dadpur District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001262/2023-2024 | 4507/ED | 23/11/2023 | 21/02/2024 | KARUNAMOY ENGINEERING | 10.74 | 4.07 | 37.93 | 90
2 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF AKNA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/18943 | Augmentation | Providing Functional House Hold Tap Connection (FHTC) under JJM withing left out portion of AKNA PWSS under Chinsurah Sub Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000728/2023-2024 | 12/CH | 04/01/2024 | 19/01/2024 | M/S BIMAL DAS AND CO. | 4.99 | 4.98 | 99.85 | 50
3 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF AKNA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/18943 | Augmentation | Quotation for new service connection at Akna(S. Aug.) W/S Sch.[SM/18943], T/W No. - III, Barol Chowmatha, Block - Polba-Dadpur, Dist. - Hooghly under Mogra CCC, WBSEDCL, Ref. Id. - 503586679, Dt. - 27-03-2024, Application No. - 5004053218 |  |  | BILL/00015/2024-2025 | 14 | 04/04/2024 | 04/04/2024 | WBSEDCL | 7.46 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF AKNA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/18943 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at AYMA NABABPUR (2Nos.), DUMURDAHA (1No.), AKNA (1 No.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000609/2023-2024 | 3356/HUG | 21/11/2023 | 05/11/2025 | AYUSH ENTERPRISE | 58.97 | 0 | 0 | 80
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF AKNA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/18943 | Augmentation | Construction of Approach Road for 3rd TW site of Akna PWSS in JJM under Polba Dadpur Block under Hooghly Division under Chinsurah Sub-Division PHE Dte | Assistant Engineer (Civil) |  | ORD/002017/2024-2025 | 316/CH | 21/02/2025 | 08/03/2025 | ASHA ENTERPRISE | 4.99 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF AKNA PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/18943 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at AYMA NABABPUR (2Nos.), DUMURDAHA (1No.), AKNA (1 No.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill),Pandua Block Junior Engineer (Civill) | ORD/000620/2023-2024 | 3386/HUG | 22/11/2023 | 30/12/2024 | OSMAN SEKH | 87.81 | 16.8 | 19.14 | 50
Total | [13 empty] | 174.97 | 25.86 | 14.78