## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18944 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at JAMGRAM (2Nos.), PANDUA (2Nos.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) |  | ORD/000584/2023-2024 | 3242/HUG | 06/11/2023 | 05/01/2024 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 59.67 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18944 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at JAMGRAM (2Nos.), PANDUA (2Nos.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000619/2023-2024 | 3384/HUG | 22/11/2023 | 01/11/2025 | MS D.PALIT AND CO. | 87.87 | 0 | 0 | 80
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18944 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at AYMA NABABPUR (2Nos.), DUMURDAHA (1No.), AKNA (1 No.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000609/2023-2024 | 3356/HUG | 21/11/2023 | 05/11/2025 | AYUSH ENTERPRISE | 58.97 | 0 | 0 | 80
4 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18944 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME Block- Dhaniakhali District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer 2 | Junior Engineer1 | ORD/001263/2023-2024 | 4508/ED | 23/11/2023 | 21/02/2024 | GLACIER ENGINEERING CO. | 21.74 | 16.12 | 74.15 | 35
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18944 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at AYMA NABABPUR (2Nos.), DUMURDAHA (1No.), AKNA (1 No.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill),Pandua Block Junior Engineer (Civill) | ORD/000620/2023-2024 | 3386/HUG | 22/11/2023 | 30/12/2024 | OSMAN SEKH | 87.81 | 17.31 | 19.72 | 50
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18944 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Kedranagar village under Dhaniakhali Block, Acharpara village of Pandua Block and Balarampur village of PAndua Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000987/2023-2024 | 261/CH | 14/03/2024 | 21/03/2024 | R.K. TRADERS | 0.95 | 0.95 | 100 | 100
7 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18944 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Sarbanandapur village under Dhaniakhali Block, Uttar Mogalpur village of Dhnaiakhali Block and Chandpur village of Dhaniakhali Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000986/2023-2024 | 260/CH | 14/03/2024 | 21/03/2024 | R.K. TRADERS | 0.95 | 0.95 | 100 | 100
8 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18944 | Augmentation | Emergency shifting of laying distribution pipeline with restoring the damages of LDS at BHADURPUR Piped Water Supply Scheme under Dhaniakhali Block due to widening & restoration of Road with construction of culvert at Belmuri-Bhanderhati Road by PWD under Chinsurah Sub-Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000464/2024-2025 | 1736/CH | 23/12/2024 | 30/12/2024 | B.S. ENTERPRISE | 3.11 | 0 | 0 | 60
9 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18944 | Augmentation | Electric quot. of WBSEDCL for New service Connection of Bahadurpur T/W-III W/S scheme under Electrical Division PHE Dte. (SM/18944) |  |  | BILL/01966/2024-2025 | 477 | 01/10/2024 | 01/10/2024 | WBSEDCL | 5.51 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18944 | Augmentation | REPAIRING & RENOVATION OF RCC OVERHEAD RESERVOIR AT HEAD WORKS SITE OF BAHADURPUR WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURAH SUB-DIVISION UNDER HOOGHLY DIVISION, PHE DTE. | Assistant Engineer (Civil) |  | ORD/001855/2024-2025 | 234/CH | 19/02/2025 | 01/03/2025 | B.S. ENTERPRISE | 4.85 | 0 | 0 | 0
Total | [13 empty] | 331.45 | 35.34 | 10.66