## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18945 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at JAMGRAM (2Nos.), PANDUA (2Nos.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) |  | ORD/000584/2023-2024 | 3242/HUG | 06/11/2023 | 05/01/2024 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 59.67 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18945 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at JAMGRAM (2Nos.), PANDUA (2Nos.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000619/2023-2024 | 3384/HUG | 22/11/2023 | 01/11/2025 | MS D.PALIT AND CO. | 87.87 | 0 | 0 | 80
3 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18945 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001264/2023-2024 | 4509/ED | 23/11/2023 | 21/02/2024 | HINDUSTAN ENGINEERING CORPORATION (E&M) | 22.05 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18945 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Benipukur Mini PWSS 2. Baro Nekua Mini PWSS 3. Muragacha (Bakulia) Mini PWSS 4. Arji Aschitpur Mini PWSS 5. Jamgram Mondalai Arsenic PWSS 6. Illampur Arsenic PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000832/2023-2024 | 210/CH | 29/02/2024 | 07/03/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 45
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18945 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Jamgram village under Pandua Block, Mandalai village of Pandua Block and Sadhat village of Pandua Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000988/2023-2024 | 262/CH | 14/03/2024 | 21/03/2024 | R.K. TRADERS | 0.95 | 0.95 | 100 | 100
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18945 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Jamgram PWSS 2. Pandua Z-I PWSS 3. Pandua Z-II PWSS 4. Pandua Z-III PWSS 5. Shibrai PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000829/2023-2024 | 207/CH | 29/02/2024 | 07/03/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.79 | 0.79 | 100 | 50
7 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18945 | Augmentation | Repairing & Renovation of Switch room and Store room at H/W Site of Jamgram PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) |  | ORD/001874/2024-2025 | 242/CH | 19/02/2025 | 01/03/2025 | M/S BIMAL DAS AND CO. | 3.07 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18945 | Augmentation | Repairing & Renovation of Switch room at PH-3 of Jamgram PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) |  | ORD/001924/2024-2025 | 273/CH | 20/02/2025 | 02/03/2025 | M/S BIMAL DAS AND CO. | 1.4 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18945 | Augmentation | Repairing & Renovation of Switch room at PH-2 of Jamgram PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) |  | ORD/001914/2024-2025 | 265/CH | 20/02/2025 | 02/03/2025 | M/S BIMAL DAS AND CO. | 1.56 | 0 | 0 | 0
10 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18945 | Augmentation | Quotation for new service connection for source Augmentation of JAMGRAM Water Supply Scheme, TW NO-V in the district Hooghly under Electrical Division, PHE Dte. ( SM/18945 ), Reference Id- 503873506 Application no- 5004581440 |  |  | BILL/03123/2024-2025 | 704 | 17/03/2025 | 17/03/2025 | WBSEDCL | 3.64 | 0 | 0 | 0
11 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18945 | Augmentation | Quotation for new service connection for source Augmentation of JAMGRAM Water Supply Scheme, TW NO-VI in the district Hooghly under Electrical Division, PHE Dte. ( SM/18945 ), Reference Id- 503873007 Application no- 5004581407 |  |  | BILL/03122/2024-2025 | 705 | 17/03/2025 | 17/03/2025 | WBSEDCL | 4.6 | 0 | 0 | 0
Total | [13 empty] | 186.55 | 2.7 | 1.45