## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18946 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at JAMGRAM (2Nos.), PANDUA (2Nos.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) |  | ORD/000584/2023-2024 | 3242/HUG | 06/11/2023 | 05/01/2024 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 59.67 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18946 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at JAMGRAM (2Nos.), PANDUA (2Nos.), BAHADURPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000619/2023-2024 | 3384/HUG | 22/11/2023 | 01/11/2025 | MS D.PALIT AND CO. | 87.87 | 0 | 0 | 80
3 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18946 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001265/2023-2024 | 4510/ED | 23/11/2023 | 21/02/2024 | INDIA ENTERPRISE | 21.48 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18946 | Augmentation | Repairing & Renovation of boundary wall and Land development at H/W Site of Pandua Z-II PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001953/2024-2025 | 275/CH | 20/02/2025 | 02/03/2025 | JOY GURU ENTERPRISE | 4.78 | 0 | 0 | 100
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18946 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at H/W Site of Pandua Z-III PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001921/2024-2025 | 271/CH | 20/02/2025 | 02/03/2025 | TOTON MONDAL | 3.38 | 0 | 0 | 100
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18946 | Augmentation | Repairing & Renovation of Switch room and Store room at H/W Site of Pandua Z-II PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001959/2024-2025 | 281/CH | 20/02/2025 | 02/03/2025 | TOTON MONDAL | 3.18 | 0 | 0 | 100
7 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18946 | Augmentation | Repairing & Renovation of Switch room and Store room at H/W Site of Pandua Z-I PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001956/2024-2025 | 278/CH | 20/02/2025 | 02/03/2025 | TOTON MONDAL | 2.84 | 0 | 0 | 100
8 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18946 | Augmentation | Repairing & Renovation of Switch room at PH-2 of Pandua Z-I PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001957/2024-2025 | 279/CH | 20/02/2025 | 02/03/2025 | JOY GURU ENTERPRISE | 2.23 | 0 | 0 | 100
9 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18946 | Augmentation | Repairing & Renovation of boundary wall and Land development at H/W Site of Pandua Z-I PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001859/2024-2025 | 238/CH | 19/02/2025 | 01/03/2025 | JOY GURU ENTERPRISE | 4.78 | 0 | 0 | 100
10 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18946 | Augmentation | Repairing & Renovation of Switch room at PH-3 of Pandua Z-I PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000001/2025-2026 | 483/CH | 04/04/2025 | 14/04/2025 | TOTON MONDAL | 1.4 | 0 | 0 | 100
11 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18946 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at PH-3 of Pandua Z-II PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001961/2024-2025 | 283/CH | 20/02/2025 | 02/03/2025 | JOY GURU ENTERPRISE | 2.9 | 0 | 0 | 100
12 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18946 | Augmentation | Emargency replacement of valves and allied works at Pandua Water Supply Scheme under Pandua Block under Chinsurah sub-division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002016/2024-2025 | 304/CH | 20/02/2025 | 02/03/2025 | JOY GURU ENTERPRISE | 3.26 | 0 | 0 | 100
13 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18946 | Augmentation | Repairing & Renovation of boundary wall, Switch room and Land development at PH-2 of Pandua Z-II PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000003/2025-2026 | 485/CH | 04/04/2025 | 14/04/2025 | JOY GURU ENTERPRISE | 1.72 | 0 | 0 | 100
14 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18946 | Augmentation | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under PANDUA Block of Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001964/2024-2025 | 286/CH | 20/02/2025 | 02/03/2025 | ASHA ENTERPRISE | 4.83 | 0 | 0 | 100
15 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18946 | Augmentation | Quotation for new service connection for source Augmentation of Pandua Water Supply Scheme, Z-II, TW NO-IV in the district Hooghly under Electrical Division,PHEDte. ( SM/18946), Reference Id- 503956018, Application no- 5004713083 |  |  | BILL/00560/2025-2026 | 42151 | 30/07/2025 | 30/07/2025 | WBSEDCL | 8.12 | 0 | 0 | 0
Total | [13 empty] | 212.46 | 0 | 0