## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block | SM/18948 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at HANRAL (2Nos.), SUDARSHAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) |  | ORD/000585/2023-2024 | 3243/HUG | 06/11/2023 | 05/01/2024 | AMBIAN INFRASTRUCTURE | 59.26 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block | SM/18948 | Augmentation | Preparation of DPR for Augmentation HANRAL Z-II Piped Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-POLBA DADPUR]. | Assistant Engineer (Civil) |  | ORD/000076/2024-2025 | 691/CH | 09/08/2024 | 16/08/2024 | APEX ENGINEERING | 4.03 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block | SM/18948 | Augmentation | Laying of UPVC Pipe At damaged portion of distribution system due to widening of road At Maheswarpur of Hanral W/S Scheme under Chinsurah Sub Division of Hooghly division, P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000887/2023-2024 | 811/HUG | 11/03/2024 | 10/04/2024 | M/S BIMAL DAS AND CO. | 9.75 | 9.69 | 99.39 | 80
4 | HOOGHLY |  | Hooghly Division | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block | SM/18948 | Augmentation | Laying of UPVC Pipe At damaged portion of distribution system due to widening of road At Rashulpur of Hanral W/S Scheme under Chinsurah Sub Division of Hooghly division, P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000886/2023-2024 | 810/HUG | 11/03/2024 | 10/04/2024 | M/S BIMAL DAS AND CO. | 9.01 | 8.94 | 99.28 | 80
5 | HOOGHLY |  | Electrical | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block | SM/18948 | Augmentation | Quotation for new service connection for Hanral (S.Aug) T.W. - I [SM/18948] (Sekendarpur), Block - Polba-Dadpur, Dt. - Hooghly under WBSEDCL, Dadpur CCC, Ref. Id. -503739105, Dt. - 21-11-2024, Application No. - 5004394547 |  |  | BILL/02479/2024-2025 | 617 | 05/12/2024 | 05/12/2024 | WBSEDCL | 4.17 | 0 | 0 | 0
6 | HOOGHLY |  | Electrical | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block | SM/18948 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of HANRAL Piped Water Supply Scheme Block- Polba-Dadpur District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001267/2023-2024 | 4512/ED | 23/11/2023 | 14/08/2025 | KUSHANI ENTERPRISE | 10.74 | 0 | 0 | 30
7 | HOOGHLY |  | Electrical | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block | SM/18948 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Hanral water supply scheme, Zone-II, T.W. No. III, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001951/2023-2024 | 90/ED | 10/01/2024 | 03/07/2025 | WIZARDTECH SOLUTION | 10.68 | 0 | 0 | 90
8 | HOOGHLY |  | Hooghly Division | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block | SM/18948 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at HANRAL (2Nos.), SUDARSHAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000626/2023-2024 | 3404/HUG | 23/11/2023 | 31/07/2025 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 86.4 | 13.97 | 16.17 | 40
Total | [13 empty] | 194.03 | 32.6 | 16.8