## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block | SM/18948 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at HANRAL (2Nos.), SUDARSHAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) |  | ORD/000585/2023-2024 | 3243/HUG | 06/11/2023 | 05/01/2024 | AMBIAN INFRASTRUCTURE | 59.26 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block | SM/18948 | Augmentation | Preparation of DPR for Augmentation HANRAL Z-II Piped Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-POLBA DADPUR]. | Assistant Engineer (Civil) |  | ORD/000076/2024-2025 | 691/CH | 09/08/2024 | 16/08/2024 | APEX ENGINEERING | 4.03 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block | SM/18948 | Augmentation | Laying of UPVC Pipe At damaged portion of distribution system due to widening of road At Maheswarpur of Hanral W/S Scheme under Chinsurah Sub Division of Hooghly division, P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000887/2023-2024 | 811/HUG | 11/03/2024 | 10/04/2024 | M/S BIMAL DAS AND CO. | 9.75 | 0 | 0 | 80
4 | HOOGHLY |  | Hooghly Division | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block | SM/18948 | Augmentation | Laying of UPVC Pipe At damaged portion of distribution system due to widening of road At Rashulpur of Hanral W/S Scheme under Chinsurah Sub Division of Hooghly division, P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000886/2023-2024 | 810/HUG | 11/03/2024 | 10/04/2024 | M/S BIMAL DAS AND CO. | 9.01 | 0 | 0 | 80
5 | HOOGHLY |  | Electrical | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block | SM/18948 | Augmentation | Quotation for new service connection for Hanral (S.Aug) T.W. - I [SM/18948] (Sekendarpur), Block - Polba-Dadpur, Dt. - Hooghly under WBSEDCL, Dadpur CCC, Ref. Id. -503739105, Dt. - 21-11-2024, Application No. - 5004394547 |  |  | BILL/02479/2024-2025 | 617 | 05/12/2024 | 05/12/2024 | WBSEDCL | 4.17 | 0 | 0 | 0
6 | HOOGHLY |  | Electrical | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block | SM/18948 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of HANRAL Piped Water Supply Scheme Block- Polba-Dadpur District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001267/2023-2024 | 4512/ED | 23/11/2023 | 14/08/2025 | KUSHANI ENTERPRISE | 10.74 | 0 | 0 | 30
7 | HOOGHLY |  | Electrical | Source Augmentation of HANRAL Piped Water Supply Scheme under Polba Dadpur Block | SM/18948 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Hanral water supply scheme, Zone-II, T.W. No. III, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001951/2023-2024 | 90/ED | 10/01/2024 | 03/07/2025 | WIZARDTECH SOLUTION | 10.68 | 0 | 0 | 90
Total | [13 empty] | 107.64 | 0 | 0