## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of SUDARSHAN Piped W/S Scheme Under Polba Dadpur Block. | SM/18949 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at HANRAL (2Nos.), SUDARSHAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) |  | ORD/000585/2023-2024 | 3243/HUG | 06/11/2023 | 05/01/2024 | AMBIAN INFRASTRUCTURE | 59.26 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of SUDARSHAN Piped W/S Scheme Under Polba Dadpur Block. | SM/18949 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed for Sajal Gram Display Board at different locations in 6 (Six) Nos villages & HGJ villages of Sudarshan PWSS for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000804/2023-2024 | 148/CH | 20/02/2024 | 27/02/2024 | R.K. TRADERS | 0.95 | 0 | 0 | 50
3 | HOOGHLY |  | Electrical | Source Augmentation of SUDARSHAN Piped W/S Scheme Under Polba Dadpur Block. | SM/18949 | Augmentation | Quotation for new service connection at Sudarshan Water Supply Scheme [SM/18949](S.Aug.),T.W. No. - III, sarangpur, Block - Polba-Dadpur, Dt. - Hooghly, under Polba CCC, Ref. Id. - 503787954, Application No. - 5004461023, Dt.-11-11-2024 |  |  | BILL/02277/2024-2025 | BP-24-25-582 | 19/11/2024 | 19/11/2024 | WBSEDCL | 6.27 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Source Augmentation of SUDARSHAN Piped W/S Scheme Under Polba Dadpur Block. | SM/18949 | Augmentation | Replacement of damaged pipe line with HDPE & CI/DI pipeline and Shifting House Connection from existing main to new main for smooth operation of water supply at Sudarshan Piped Water Supply Scheme of Chinsurah Sub-Division under Hooghly Division, PHE Dte. |  |  | ORD/001833/2024-2025 | 330/HUG | 05/02/2025 | 07/03/2025 | RAJ CONSTRUCTION | 7.01 | 0 | 0 | 0
Total | [13 empty] | 73.49 | 0 | 0