## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation Of AMRA Piped W/S Scheme under Polba Dadbur Block | SM/18950 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at HANRAL (2Nos.), SUDARSHAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) |  | ORD/000585/2023-2024 | 3243/HUG | 06/11/2023 | 05/01/2024 | AMBIAN INFRASTRUCTURE | 59.26 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | Source Augmentation Of AMRA Piped W/S Scheme under Polba Dadbur Block | SM/18950 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of AMRA Piped W/S Scheme Block- Polba-Dadpur District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001274/2023-2024 | 4514/ED | 23/11/2023 | 21/02/2024 | SRI KRISHNA NIRMAN | 21.5 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Source Augmentation Of AMRA Piped W/S Scheme under Polba Dadbur Block | SM/18950 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement ,Laying rising main pipe for inter connection between Proposed T.W & Distribution of AMRA Piped Water Supply Scheme under CHINSURAH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000567/2023-2024 | 3192/HUG | 31/10/2023 | 30/12/2023 | R.K. TRADERS | 7.56 | 6.57 | 86.91 | 100
4 | HOOGHLY |  | Hooghly Division | Source Augmentation Of AMRA Piped W/S Scheme under Polba Dadbur Block | SM/18950 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at PAUNAN (2Nos.), PUINAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000586/2023-2024 | 3244/HUG | 06/11/2023 | 05/01/2024 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 59.57 | 0 | 0 | 45
5 | HOOGHLY |  | Electrical | Source Augmentation Of AMRA Piped W/S Scheme under Polba Dadbur Block | SM/18950 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Amra water supply scheme, T.W. No. III, Block: Polba Dadpur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000032/2022-2023 | 1914/ED | 21/11/2022 | 19/02/2023 | M/S MANABESH ROY | 9.39 | 9.1 | 96.86 | 98
6 | HOOGHLY |  | Hooghly Division | Source Augmentation Of AMRA Piped W/S Scheme under Polba Dadbur Block | SM/18950 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at PAUNAN (2Nos.), PUINAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000628/2023-2024 | 3405/HUG | 23/11/2023 | 16/06/2025 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 86.4 | 0 | 0 | 25
7 | HOOGHLY |  | Hooghly Division | Source Augmentation Of AMRA Piped W/S Scheme under Polba Dadbur Block | SM/18950 | Augmentation | Repairing of existing Switch room(5.4 M X3.6M)& Boundary wall at existing OHR Site of AMRA Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at POLBA DADPUR Block | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001467/2024-2025 | 131/CH | 29/01/2025 | 01/03/2025 | ASHA ENTERPRISE | 4.62 | 0 | 0 | 50
Total | [13 empty] | 248.29 | 15.66 | 6.31