## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation Of Paunan Water Supply Scheme Under Polba Dadpur Block | SM/18951 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at PAUNAN (2Nos.), PUINAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) |  | ORD/000586/2023-2024 | 3244/HUG | 06/11/2023 | 05/01/2024 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 59.57 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Source Augmentation Of Paunan Water Supply Scheme Under Polba Dadpur Block | SM/18951 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed for Sajal Gram Display Board at different locations in 6 (six) Nos villages & HGJ villages of Paunan PWSS for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000801/2023-2024 | 144/CH | 20/02/2024 | 27/02/2024 | R.K. TRADERS | 0.95 | 0.48 | 50 | 50
3 | HOOGHLY |  | Hooghly Division | Source Augmentation Of Paunan Water Supply Scheme Under Polba Dadpur Block | SM/18951 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at PAUNAN (2Nos.), PUINAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000628/2023-2024 | 3405/HUG | 23/11/2023 | 07/01/2024 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 86.4 | 6.76 | 7.82 | 25
4 | HOOGHLY |  | Electrical | Source Augmentation Of Paunan Water Supply Scheme Under Polba Dadpur Block | SM/18951 | Augmentation | Quotation for new service connection at Pownan W/S Sch. , (S. Aug.),[SM/18951] T/W No. - IV, Bihari Pally, Block - Polba-Dadpur, Dist. Hooghly, under SM/Polba, WBSEDCL, Ref. Id. - 503594866, Dt. - 02-04-2024, Application No. - 5004069653 |  |  | BILL/00077/2024-2025 | 39 | 09/04/2024 |  | WBSEDCL | 4.2 | 0 | 0 | null
5 | HOOGHLY |  | Hooghly Division | Source Augmentation Of Paunan Water Supply Scheme Under Polba Dadpur Block | SM/18951 | Augmentation | Sinking of 1no 300 X200 mm dia Tube Well 210 mtr. Depth by tube-well by D.R. Rig method for using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) to replace the exsisting T.W at head work site of Paonan Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) |  | ORD/000053/2024-2025 | 2344/HUG | 19/06/2024 | 19/07/2024 | BANSBERIA CONSTRUCTION CO. | 16.03 | 0 | 0 | 0
6 | HOOGHLY |  | Electrical | Source Augmentation Of Paunan Water Supply Scheme Under Polba Dadpur Block | SM/18951 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of Paunan Water Supply Scheme Block- Polba-Dadpur District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001275/2023-2024 | 4515/ED | 23/11/2023 | 21/02/2024 | S.S. ENTERPRISES | 21.91 | 0 | 0 | 50
Total | [13 empty] | 189.06 | 7.23 | 3.83