## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation Of PUINAN piped Water Supply Scheme Under Polba Dadpur Block | SM/18952 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at PAUNAN (2Nos.), PUINAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000586/2023-2024 | 3244/HUG | 06/11/2023 | 05/01/2024 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 59.57 | 0 | 0 | 45
2 | HOOGHLY |  | Hooghly Division | Source Augmentation Of PUINAN piped Water Supply Scheme Under Polba Dadpur Block | SM/18952 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at PAUNAN (2Nos.), PUINAN (2Nos.), AMRA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000628/2023-2024 | 3405/HUG | 23/11/2023 | 16/06/2025 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 86.4 | 28.08 | 32.5 | 25
3 | HOOGHLY |  | Electrical | Source Augmentation Of PUINAN piped Water Supply Scheme Under Polba Dadpur Block | SM/18952 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of PUINAN piped Water Supply Scheme Block- Polba-Dadpur District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001276/2023-2024 | 4516/ED | 23/11/2023 | 21/02/2024 | SUTRADHAR TRADERS | 21.47 | 6.16 | 28.7 | 30
4 | HOOGHLY |  | Hooghly Division | Source Augmentation Of PUINAN piped Water Supply Scheme Under Polba Dadpur Block | SM/18952 | Augmentation | Replacement of damaged pipe line with HDPE pipeline and Shifting House Connection from existing main to new main at Ser Gram of Puinan Piped Water Supply Scheme of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000046/2024-2025 | 549/CH | 14/06/2024 | 21/06/2024 | MAA BUNAMATA ENTERPRISE | 5 | 4.99 | 99.87 | 80
5 | HOOGHLY |  | Hooghly Division | Source Augmentation Of PUINAN piped Water Supply Scheme Under Polba Dadpur Block | SM/18952 | Augmentation | Replacement of damaged pipe line with HDPE pipeline and Shifting House Connection from existing main to new main at Tin MandirTala of Puinan Piped Water Supply Scheme of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000047/2024-2025 | 550/CH | 14/06/2024 | 21/06/2024 | MAA BUNAMATA ENTERPRISE | 4.97 | 4.97 | 100 | 80
6 | HOOGHLY |  | Hooghly Division | Source Augmentation Of PUINAN piped Water Supply Scheme Under Polba Dadpur Block | SM/18952 | Augmentation | Replacement of damaged pipe line with HDPE pipeline and Shifting House Connection from existing main to new main at Puinan Piped Water Supply Scheme of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000463/2024-2025 | 1735/CH | 23/12/2024 | 21/02/2025 | MAA BUNAMATA ENTERPRISE | 2.43 | 0.64 | 26.45 | 50
7 | HOOGHLY |  | Hooghly Division | Source Augmentation Of PUINAN piped Water Supply Scheme Under Polba Dadpur Block | SM/18952 | Augmentation | DAMAGE DUE TO LAY OF PHE PIPELINE FOR THE WORK NAMELY CONSTRUCTION OF ROAD FROM KANTAGORI TO PUINAN TINMANDIRTALA UNDER POLBA DADPUR BLOCK. |  |  | BILL/00362/2024-2025 | BP-2024-25-292 | 10/07/2024 | 10/07/2024 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 8.11 | 0 | 0 | 0
8 | HOOGHLY |  | Electrical | Source Augmentation Of PUINAN piped Water Supply Scheme Under Polba Dadpur Block | SM/18952 | Augmentation | Quotation for new servce connection at Puinan (S.Aug.) [SM/18952] , T/W No. - III, Block - Polba-Dadpur, Dist. - Hooghly under Dadpur CCC, WBSEDCL, Ref, Id. - 503619158, Dt. - 13-05-2024, Application No. - 5004116682 |  |  | BILL/00450/2024-2025 | 124 | 17/05/2024 | 17/05/2024 | WBSEDCL | 3.22 | 0 | 0 | 0
9 | HOOGHLY |  | Electrical | Source Augmentation Of PUINAN piped Water Supply Scheme Under Polba Dadpur Block | SM/18952 | Augmentation | Quotation for new servce connection at Puinan (S.Aug.) [SM/18952] , T/W No. - IV, Block - Polba-Dadpur, Dist. - Hooghly under Dadpur CCC, WBSEDCL, Ref, Id. - 503619159, Dt. - 13-05-2024, Application No. - 5004116723 |  |  | BILL/00451/2024-2025 | 122 | 17/05/2024 | 17/05/2024 | WBSEDCL | 6.36 | 0 | 0 | 0
Total | [13 empty] | 197.52 | 44.85 | 22.7