## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation Of GOSWAMI MALIPARA Piped Water Supply Scheme Under POlba Dadpur Block | SM/18953 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at GOSWAMI MALIPARA (1 No.), NALDANGA (2 Nos.), KEOTA (1 No.), HASAMPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000631/2023-2024 | 3406/HUG | 23/11/2023 | 07/01/2024 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 86.4 | 27.84 | 32.23 | 50
2 | HOOGHLY |  | Electrical | Source Augmentation Of GOSWAMI MALIPARA Piped Water Supply Scheme Under POlba Dadpur Block | SM/18953 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of GOSWAMI MALIPARA Piped Water Supply Scheme Block- Polba-Dadpur District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001277/2023-2024 | 4517/ED | 23/11/2023 | 21/02/2024 | APEX ENGINEERING & PROJECT CO. | 10.74 | 0 | 0 | 90
3 | HOOGHLY |  | Hooghly Division | Source Augmentation Of GOSWAMI MALIPARA Piped Water Supply Scheme Under POlba Dadpur Block | SM/18953 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Malipara village under Polba Dadpur Block, Manipur village of Polba Dadpur Block and Prasadpur village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000991/2023-2024 | 265/CH | 14/03/2024 | 21/03/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 100
4 | HOOGHLY |  | Electrical | Source Augmentation Of GOSWAMI MALIPARA Piped Water Supply Scheme Under POlba Dadpur Block | SM/18953 | Augmentation | Quotation for new service connection at Goswamimalipara (Aug.) [SM/18953] W/s Sch., T/W No. - IV, Village & P. O. - Shenet, Dt. - Hooghly under Dadpur CCC, WBSEDCL, Ref. Id. - 503669411, Dt. - 11-07-2024, Application No. - 5004243696 |  |  | BILL/01190/2024-2025 | 311 | 22/07/2024 | 22/07/2024 | WBSEDCL | 3.44 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | Source Augmentation Of GOSWAMI MALIPARA Piped Water Supply Scheme Under POlba Dadpur Block | SM/18953 | Augmentation | Quotation for new service connection at Goswamimalipara (Aug.)[SM/18953] W/S Sch., T/W No. - III, Block - Polba-dadpur, under Dadpur CCC, WBSEDCL, Ref Id. - 503619160, dt. - 25-06-2024, Application No. - 5004116875. |  |  | BILL/01141/2024-2025 | 263 | 03/07/2024 | 03/07/2024 | WBSEDCL | 9.13 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Source Augmentation Of GOSWAMI MALIPARA Piped Water Supply Scheme Under POlba Dadpur Block | SM/18953 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at GOSWAMI MALIPARA (1 No.), NALDANGA (2 Nos.), KEOTA (1 No.), HASAMPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000587/2023-2024 | 3245/HUG | 06/11/2023 | 28/06/2025 | TAPAS ADHYA | 59.64 | 0 | 0 | 20
Total | [13 empty] | 170.3 | 28.8 | 16.91