## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block | SM/18954 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at GOSWAMI MALIPARA (1 No.), NALDANGA (2 Nos.), KEOTA (1 No.), HASAMPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000631/2023-2024 | 3406/HUG | 23/11/2023 | 07/01/2024 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 86.4 | 0 | 0 | 50
2 | HOOGHLY |  | Electrical | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block | SM/18954 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of NALDANGA piped W/S Scheme Block- ChinsurahMogra District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001278/2023-2024 | 4518/ED | 23/11/2023 | 21/02/2024 | SUBHRA ENTERPRISE | 21.49 | 8.24 | 38.34 | 70
3 | HOOGHLY |  | Electrical | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block | SM/18954 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Naldanga w/s scheme, T.W No. V, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/001171/2023-2024 | 4444/ED | 17/11/2023 | 15/02/2024 | MOITRA ENGINEERING CO. | 10.92 | 9.97 | 91.28 | 90
4 | HOOGHLY |  | Hooghly Division | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block | SM/18954 | Augmentation | Providing and installation of 150 mm x 100 mm dia. tubewell by Rig Bored system with Switch Room and allied works at Madrasi Para Under Naldanga Piped Water Supply Scheme In Chinsurah Sub-Division Of Hooghly Division, P.H.E. Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000669/2023-2024 | 3564/HUG | 05/12/2023 | 04/01/2024 | SOUMYADIP DE | 16.51 | 12.95 | 78.48 | 50
5 | HOOGHLY |  | Hooghly Division | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block | SM/18954 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Kola PWSS 2. Kulihanda PWSS 3. Madhusudanpur PWSS 4. Naldanga PWSS 5. Raghunathpur PWSS 6. Refaitpur Z-I PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000821/2023-2024 | 199/CH | 29/02/2024 | 07/03/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0.95 | 100 | 50
6 | HOOGHLY |  | Hooghly Division | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block | SM/18954 | Augmentation | Providing FHTC at the left out portions of Different area for proiving FHTC in Kulihanda, Naldanga & Debanandapur Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000038/2024-2025 | 540/CH | 14/06/2024 | 21/06/2024 | MAA BUNAMATA ENTERPRISE | 4.85 | 4.85 | 99.93 | 80
7 | HOOGHLY |  | Electrical | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block | SM/18954 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for NALDANGA MINI W/S SCHEME, Block: Chinsura Mogra, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000169/2024-2025 | 1192/ED | 14/06/2024 | 12/09/2024 | TULIP ENTERPRISE | 7.53 | 7.41 | 98.42 | 95
8 | HOOGHLY |  | Electrical | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block | SM/18954 | Augmentation | Quotation for additional quotation for Naldanga(S.Aug.) W/s Sch., T.W. No. - VII [SM/18954], Ref Id- 860316928, Application Id. - 100000122348, dt. - 30-10-2024 |  |  | BILL/02128/2024-2025 | 567 | 13/11/2024 | 13/11/2024 | WBSEDCL | 0.81 | 0 | 0 | 0
9 | HOOGHLY |  | Electrical | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block | SM/18954 | Augmentation | Quotation for new service connection at Naldanga(S.Aug.) [SM/18954], T/W NO. - I, under Pipulpati CCC, WBSEDCL, Ref. Id. - 503644538, dt.- 14-05-2024, Application No. - 5004183039 |  |  | BILL/00539/2024-2025 | 181 | 30/05/2024 | 30/05/2024 | WBSEDCL | 8.65 | 0 | 0 | 0
10 | HOOGHLY |  | Electrical | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block | SM/18954 | Augmentation | Quotation for new service connection at Naldanga (Source Aug.) water supply Scheme [SM/18954], T/W No. - VI(Mini), Block - Chinsurah-Mogra, under Bandel CCC, WBSEDCL, Ref. Id. - 503582004, Dt. - 29-02-2024, Application No. - 5004045934 |  |  | BILL/06281/2023-2024 | 878 | 13/03/2024 | 13/03/2024 | WBSEDCL | 4.35 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block | SM/18954 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at GOSWAMI MALIPARA (1 No.), NALDANGA (2 Nos.), KEOTA (1 No.), HASAMPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000587/2023-2024 | 3245/HUG | 06/11/2023 | 28/06/2025 | TAPAS ADHYA | 59.64 | 0 | 0 | 20
12 | HOOGHLY |  | Hooghly Division | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block | SM/18954 | Augmentation | Construction of approach Road for Head Works site of NALDANGA piped water supply scheme in JJM under Chinsurah-Mogra Block. | Assistant Engineer (Civil) |  | ORD/002387/2024-2025 | 376/CH | 04/03/2025 | 11/03/2025 | DUTTA CONSTRUCTION | 0.94 | 0 | 0 | 0
13 | HOOGHLY |  | Hooghly Division | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block | SM/18954 | Augmentation | Emergency replacement of valves and allied works at Kulihanda, Darampur & Naldanga Water Supply Scheme under Chinsurah sub-division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001854/2024-2025 | 233/CH | 19/02/2025 | 31/05/2025 | SOUMYADIP DE | 4.01 | 0 | 0 | 100
14 | HOOGHLY |  | Electrical | Source Augmentation Of NALDANGA piped W/S Scheme Under Chinsurah Magra Block | SM/18954 | Augmentation | Quotation for new service connection at Naldanga (S.Aug) W/S Sch., T/W No. - VIII,[SM/18954] Singibagan, Block - Chinsurah-Mogra, Dt. - Hooghly, under Bandel CCC,WBSEDCL, Ref. Id. - 503973828, Dt. -22/05/2025, Application No. - 5004750825 |  |  | BILL/01020/2025-2026 | 42151 | 30/07/2025 | 30/07/2025 | WBSEDCL | 7.89 | 0 | 0 | 0
Total | [13 empty] | 234.94 | 44.37 | 18.89