## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation Of KEOTA Piped Water Supply Scheme Under Chinsurah Magra Block | SM/18955 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at GOSWAMI MALIPARA (1 No.), NALDANGA (2 Nos.), KEOTA (1 No.), HASAMPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000587/2023-2024 | 3245/HUG | 06/11/2023 | 28/06/2025 | TAPAS ADHYA | 59.64 | 0 | 0 | 20
2 | HOOGHLY |  | Hooghly Division | Source Augmentation Of KEOTA Piped Water Supply Scheme Under Chinsurah Magra Block | SM/18955 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at GOSWAMI MALIPARA (1 No.), NALDANGA (2 Nos.), KEOTA (1 No.), HASAMPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000631/2023-2024 | 3406/HUG | 23/11/2023 | 07/01/2024 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 86.4 | 0 | 0 | 50
3 | HOOGHLY |  | Electrical | Source Augmentation Of KEOTA Piped Water Supply Scheme Under Chinsurah Magra Block | SM/18955 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of KEOTA Piped Water Supply Scheme Block- ChinsurahMogra District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001279/2023-2024 | 4519/ED | 23/11/2023 | 21/02/2024 | SUJOY RANJAN BHOWMICK | 10.74 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Source Augmentation Of KEOTA Piped Water Supply Scheme Under Chinsurah Magra Block | SM/18955 | Augmentation | Laying of pipe line for improvement of water supply in distribution system at Keota & Kulihanda W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000516/2023-2024 | 823/CH | 31/08/2023 | 15/09/2023 | M/S BIMAL DAS AND CO. | 0.96 | 0.96 | 100 | 80
5 | HOOGHLY |  | Hooghly Division | Source Augmentation Of KEOTA Piped Water Supply Scheme Under Chinsurah Magra Block | SM/18955 | Augmentation | Laying HDPE pipeline at Dunlop of KEOTA Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000072/2024-2025 | 630/CH | 15/07/2024 | 25/07/2024 | BIMAL KUMAR HALDER | 4.85 | 4.84 | 99.79 | 55
6 | HOOGHLY |  | Hooghly Division | Source Augmentation Of KEOTA Piped Water Supply Scheme Under Chinsurah Magra Block | SM/18955 | Augmentation | Laying HDPE pipeline at Dunlop and Kailashnagar of KEOTA Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001851/2024-2025 | 230/CH | 19/02/2025 | 01/03/2025 | BIMAL KUMAR HALDER | 2.92 | 0 | 0 | 100
Total | [13 empty] | 165.52 | 5.81 | 3.51