## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of HASAMPUR Piped Water Supply Scheme under Dhaniakhali Block | SM/18956 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at GOSWAMI MALIPARA (1 No.), NALDANGA (2 Nos.), KEOTA (1 No.), HASAMPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000587/2023-2024 | 3245/HUG | 06/11/2023 | 28/06/2025 | TAPAS ADHYA | 59.64 | 0 | 0 | 20
2 | HOOGHLY |  | Electrical | Source Augmentation of HASAMPUR Piped Water Supply Scheme under Dhaniakhali Block | SM/18956 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of HASAMPUR Piped Water Supply Scheme Block- Dhaniakhali District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001288/2023-2024 | 4520/ED | 23/11/2023 | 21/02/2024 | APEX ENGINEERING & PROJECT CO. | 10.74 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of HASAMPUR Piped Water Supply Scheme under Dhaniakhali Block | SM/18956 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at GOSWAMI MALIPARA (1 No.), NALDANGA (2 Nos.), KEOTA (1 No.), HASAMPUR (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000631/2023-2024 | 3406/HUG | 23/11/2023 | 07/01/2024 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 86.4 | 13.72 | 15.88 | 50
4 | HOOGHLY |  | Hooghly Division | Source Augmentation of HASAMPUR Piped Water Supply Scheme under Dhaniakhali Block | SM/18956 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in GURAP II GP of DHNIAKHALI Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000914/2023-2024 | 249/CH | 12/03/2024 | 11/04/2024 | M/S MANGALCHANDI CONSTRUCTION | 4.98 | 0 | 0 | 89
5 | HOOGHLY |  | Hooghly Division | Source Augmentation of HASAMPUR Piped Water Supply Scheme under Dhaniakhali Block | SM/18956 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas / Habitations of DIGHIR, HASAMPUR, CHERAGRAM, GURAP PWSS under DHANIAKHALI Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. |  |  | ORD/001550/2024-2025 | 323/HUG | 05/02/2025 | 02/03/2025 | SWARNA ENTERPRISE | 8.63 | 0 | 0 | 0
6 | HOOGHLY |  | Electrical | Source Augmentation of HASAMPUR Piped Water Supply Scheme under Dhaniakhali Block | SM/18956 | Augmentation | Electric quot. of WBSEDCL for New service Connection of Hasampur T/W-III W/S scheme under Electrical Division PHE Dte. (SM/18956) |  |  | BILL/03360/2024-2025 | 706 | 17/03/2025 | 17/03/2025 | WBSEDCL | 4.02 | 0 | 0 | 0
Total | [13 empty] | 174.4 | 13.72 | 7.87