## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block | SM/18958 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bachhanari water supply scheme, T.W. No. III, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001529/2021-2022 | 553_ED | 22/03/2022 | 20/06/2022 | S.M. ELECTRICALS | 6.05 | 6.05 | 100 | 50
2 | HOOGHLY |  | Electrical | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block | SM/18958 | Augmentation | Supply delivery and installation of voltage correcting device and other allied works for Bachhanari w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. |  |  | ORD/002572/2022-2023 | 659/HMSD | 04/04/2022 | 04/05/2022 | NITESH MANAGEMENT | 2.74 | 2.74 | 100 | 100
3 | HOOGHLY |  | Electrical | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block | SM/18958 | Augmentation | Supply delivery and installation of Chlorinator for Bachhanari w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. |  |  | ORD/001526/2021-2022 | 316/HMSD | 18/02/2022 | 19/05/2022 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 0.76 | 0.76 | 100 | 100
4 | HOOGHLY |  | Hooghly Division | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block | SM/18958 | Augmentation | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of SELAMPUR, BACHHANARI & SAMANTAKHANDA W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000170/2024-2025 | 3169/HUG | 10/09/2024 | 25/10/2024 | BALAJI UDDYOG | 48.46 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block | SM/18958 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BACHHANARI PIPED W/S SCHEME, T.W. No. IV, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000367/2024-2025 | 1451/ED | 25/07/2024 | 23/10/2024 | DAS ENTERPRISE | 11.08 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block | SM/18958 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) SRIRAMPUR PWSS- 3nos (2) BACHHANARI PWSS- 3nos (3) MALAYPUR PWSS- 4nos (4) MANDRA PWSS- 4nos | Assistant Engineer | Junior Engineer (Civill) | ORD/002644/2024-2025 | 807/Arg | 23/08/2024 | 22/09/2024 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block | SM/18958 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub-Division under Hooghly Division PHE Dte. (i) BACHANARI PWSS (ii) KAPSIT PWSS (iii) JOY KRISHNAPUR PWSS (iv) BALI PWSS (v) LAKSHMIPUR PWSS (vi) RADHABALLAVPUR PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000431/2024-2025 | 798/Arg | 23/08/2024 | 30/08/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0 | 0 | 100
8 | HOOGHLY |  | Hooghly Division | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block | SM/18958 | Augmentation | Repairing of Boundary Wall, Switch Room & R.C.C. Elevated Reservoir of BACHHANARI PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/002261/2024-2025 | 573/HUG | 04/03/2025 | 01/02/2026 | MS CHANDIMATA CONSTRUCTION | 12.45 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block | SM/18958 | Augmentation | Protection works and other allied works at 3rd & 4th TubeWell Site of BACCHANARI Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000439/2024-2025 | 4043/HUG | 19/12/2024 | 14/12/2025 | MS CHANDIMATA CONSTRUCTION | 15.46 | 0 | 0 | 100
Total | [13 empty] | 98.93 | 9.55 | 9.65