## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block | SM/18958 | Augmentation | Supply delivery and installation of voltage correcting device and other allied works for Bachhanari w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. |  |  | ORD/002572/2022-2023 | 659/HMSD | 04/04/2022 | 04/05/2022 | NITESH MANAGEMENT | 2.74 | 2.74 | 100 | 100
2 | HOOGHLY |  | Electrical | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block | SM/18958 | Augmentation | Supply delivery and installation of Chlorinator for Bachhanari w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. |  |  | ORD/001526/2021-2022 | 316/HMSD | 18/02/2022 | 19/05/2022 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 0.76 | 0.76 | 100 | 100
3 | HOOGHLY |  | Electrical | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block | SM/18958 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bachhanari water supply scheme, T.W. No. III, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001529/2021-2022 | 553_ED | 22/03/2022 | 20/06/2022 | S.M. ELECTRICALS | 6.05 | 4.78 | 78.88 | 50
4 | HOOGHLY |  | Electrical | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block | SM/18958 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BACHHANARI PIPED W/S SCHEME, T.W. No. IV, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000367/2024-2025 | 1451/ED | 25/07/2024 | 23/10/2024 | DAS ENTERPRISE | 11.08 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Source Augmentation of BACHHANARI Piped Water Supply Scheme Under Arambag Block | SM/18958 | Augmentation | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of SELAMPUR, BACHHANARI & SAMANTAKHANDA W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000170/2024-2025 | 3169/HUG | 10/09/2024 | 25/10/2024 | BALAJI UDDYOG | 48.46 | 0 | 0 | 0
Total | [13 empty] | 69.09 | 8.27 | 11.97