## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Source Augmentation of DIHI BAYARA Piped Water Supply Scheme Under Arambag Block | SM/18959 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Dihibayra water supply scheme, T.W. No. III, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001532/2021-2022 | 471_ED | 10/03/2022 | 08/06/2022 | T S CONSTRUCTION | 6.4 | 0 | 0 | 50
2 | HOOGHLY |  | Electrical | Source Augmentation of DIHI BAYARA Piped Water Supply Scheme Under Arambag Block | SM/18959 | Augmentation | Supply delivery and installation of voltage correcting device and other allied works for Dihibayra w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. |  |  | ORD/001527/2021-2022 | 544/HMSD | 17/03/2022 | 16/04/2022 | WIZARDTECH SOLUTION | 2.36 | 0 | 0 | 100
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of DIHI BAYARA Piped Water Supply Scheme Under Arambag Block | SM/18959 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir , Bounary Wall of DIHIBAYRA PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000383/2024-2025 | 3777/HUG | 25/11/2024 | 04/01/2025 | M/S PRADYUT KUMAR HAZRA (PARTNERSHIP) | 12.75 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Source Augmentation of DIHI BAYARA Piped Water Supply Scheme Under Arambag Block | SM/18959 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) PABA PWSS-3nos (2) DIHIBAYRA PWSS- 3nos (3) HAYATPUR PWSS- 4nos (4) RAJHATO PWSS- 4nos | Assistant Engineer | Junior Engineer (Civill) | ORD/002647/2024-2025 | 811/Arg | 23/08/2024 | 22/09/2024 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
Total | [13 empty] | 22.49 | 0 | 0