## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block | SM/18960 | Augmentation | Supply and installation of short MS casing pipe making TW foundation and S&F submersible AL. Ar. cable at Hayatpur w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. |  |  | ORD/002570/2022-2023 | 1928/HMSD | 03/11/2022 | 10/11/2022 | DAS ENTERPRISE | 0.9 | 0.9 | 100 | 100
2 | HOOGHLY |  | Electrical | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block | SM/18960 | Augmentation | Supply delivery and installation of Chlorinator for Hayatpur w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. |  |  | ORD/002571/2022-2023 | 1878/HMSD | 20/10/2022 | 27/10/2022 | DAS ENTERPRISE | 0.8 | 0.8 | 100 | 100
3 | HOOGHLY |  | Electrical | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block | SM/18960 | Augmentation | Supply delivery and installation of voltage correcting device and other allied works for Hayatpur w/s scheme PH No. IV District Hooghly under Electrical Division, PHE dte. |  |  | ORD/001524/2021-2022 | 540/HMSD | 17/03/2022 | 07/04/2022 | MOITRA ENGINEERING CO. | 2.74 | 2.74 | 100 | 100
4 | HOOGHLY |  | Electrical | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block | SM/18960 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Hayatpur water supply scheme, T.W. No. III, Block: Arambag , District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001520/2021-2022 | 472/ED | 10/03/2022 | 08/06/2022 | DAS ENTERPRISE | 6.89 | 4.08 | 59.22 | 100
5 | HOOGHLY |  | Electrical | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block | SM/18960 | Augmentation | Supply delivery and installation of voltage correcting device and other allied works for Hayatpur w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. |  |  | ORD/001525/2021-2022 | 542/HMSD | 17/03/2022 | 16/04/2022 | KASHINATH PAL & CO. | 2.74 | 2.72 | 99.29 | 100
6 | HOOGHLY |  | Electrical | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block | SM/18960 | Augmentation | Supply delivery and installation of Chlorinator for Hayatpur w/s scheme PH No. IV District Hooghly under Electrical Division, PHE dte. |  |  | ORD/002569/2022-2023 | 71/HMSD | 10/01/2023 | 17/01/2023 | S P ENTERPRISE | 0.8 | 0.8 | 100 | 100
7 | HOOGHLY |  | Electrical | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block | SM/18960 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Hayatpur water supply scheme, T.W. No. IV, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/001534/2021-2022 | 473/ED | 10/03/2022 | 08/06/2022 | S.P. ENTERPRISE | 6.92 | 6.36 | 92 | 50
Total | [13 empty] | 21.79 | 18.41 | 84.47