## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block | SM/18960 | Augmentation | Supply delivery and installation of voltage correcting device and other allied works for Hayatpur w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. |  |  | ORD/001525/2021-2022 | 542/HMSD | 17/03/2022 | 16/04/2022 | KASHINATH PAL & CO. | 2.74 | 2.72 | 99.29 | 100
2 | HOOGHLY |  | Electrical | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block | SM/18960 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Hayatpur water supply scheme, T.W. No. IV, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/001534/2021-2022 | 473/ED | 10/03/2022 | 08/06/2022 | S.P. ENTERPRISE | 6.92 | 6.36 | 92 | 50
3 | HOOGHLY |  | Electrical | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block | SM/18960 | Augmentation | Supply and installation of short MS casing pipe making TW foundation and S&F submersible AL. Ar. cable at Hayatpur w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. |  |  | ORD/002570/2022-2023 | 1928/HMSD | 03/11/2022 | 10/11/2022 | DAS ENTERPRISE | 0.9 | 0.9 | 100 | 100
4 | HOOGHLY |  | Electrical | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block | SM/18960 | Augmentation | Supply delivery and installation of Chlorinator for Hayatpur w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. |  |  | ORD/002571/2022-2023 | 1878/HMSD | 20/10/2022 | 27/10/2022 | DAS ENTERPRISE | 0.8 | 0.8 | 100 | 100
5 | HOOGHLY |  | Electrical | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block | SM/18960 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Hayatpur water supply scheme, T.W. No. III, Block: Arambag , District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001520/2021-2022 | 472/ED | 10/03/2022 | 08/06/2022 | DAS ENTERPRISE | 6.89 | 6.57 | 95.33 | 100
6 | HOOGHLY |  | Electrical | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block | SM/18960 | Augmentation | Supply delivery and installation of voltage correcting device and other allied works for Hayatpur w/s scheme PH No. IV District Hooghly under Electrical Division, PHE dte. |  |  | ORD/001524/2021-2022 | 540/HMSD | 17/03/2022 | 07/04/2022 | MOITRA ENGINEERING CO. | 2.74 | 2.74 | 100 | 100
7 | HOOGHLY |  | Electrical | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block | SM/18960 | Augmentation | Supply delivery and installation of Chlorinator for Hayatpur w/s scheme PH No. IV District Hooghly under Electrical Division, PHE dte. |  |  | ORD/002569/2022-2023 | 71/HMSD | 10/01/2023 | 17/01/2023 | S P ENTERPRISE | 0.8 | 0.8 | 100 | 100
8 | HOOGHLY |  | Hooghly Division | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block | SM/18960 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of HAYATPUR PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000455/2024-2025 | 4076/HUG | 19/12/2024 | 19/03/2025 | ROY ENTERPRISE | 11.55 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block | SM/18960 | Augmentation | Protection works and other allied works OF 3rd & 4th TubeWell Site of HAYATPUR Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte. |  |  | ORD/000443/2024-2025 | 4045/HUG | 19/12/2024 | 19/03/2025 | S D ENTERPRISE | 15.52 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block | SM/18960 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) PABA PWSS-3nos (2) DIHIBAYRA PWSS- 3nos (3) HAYATPUR PWSS- 4nos (4) RAJHATO PWSS- 4nos | Assistant Engineer | Junior Engineer (Civill) | ORD/002647/2024-2025 | 811/Arg | 23/08/2024 | 22/09/2024 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | Source Augmentation of HAYATPUR piped Water Supply Scheme Under Arambag block | SM/18960 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub-Division under Hooghly Division PHE Dte. (i) PALASPAI PWSS (ii) SABALSINGHAPUR PWSS (iii) CHINGRA (ZONE- I) PWSS (iv) CHINGRA (ZONE- II) PWSS (v) HAYATPUR PWSS (vi) PRATAPNAGAR PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000441/2024-2025 | 802/Arg | 23/08/2024 | 30/08/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0 | 0 | 100
Total | [13 empty] | 50.79 | 20.9 | 41.14