## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Source Augmentation Of BAIKUNTHAPUR piped Water Supply Scheme under Pursurah Block | SM/18961 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of BAIKUNTHAPUR piped Water Supply Scheme Block- Pursura District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001290/2023-2024 | 4522/ED | 23/11/2023 | 21/02/2024 | TRIDENT ENTERPRISE | 22.03 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Source Augmentation Of BAIKUNTHAPUR piped Water Supply Scheme under Pursurah Block | SM/18961 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at PABA (1 NO.),BAIKUNTHAPUR (2Nos.),SAOTA (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer | Junior Engineer (Civill) | ORD/000645/2023-2024 | 3475/HUG | 29/11/2023 | 13/01/2024 | CIVIL CRAFT | 88.67 | 0 | 0 | 60
3 | HOOGHLY |  | Hooghly Division | Source Augmentation Of BAIKUNTHAPUR piped Water Supply Scheme under Pursurah Block | SM/18961 | Augmentation | Construction of 3 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 3 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 3 Nos. T.W & Distribution at BAIKUNTHAPUR (1Nos.), SAOTA (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer | Junior Engineer (Civill) | ORD/000716/2023-2024 | 3352/HUG | 17/11/2023 | 03/01/2026 | A.R. CONSTRUCTION | 35.75 | 0 | 0 | 20
4 | HOOGHLY |  | Hooghly Division | Source Augmentation Of BAIKUNTHAPUR piped Water Supply Scheme under Pursurah Block | SM/18961 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub-Division under Hooghly Division PHE Dte. (i) BAIKUNTHAPUR PWSS (ii) BHANGAMORA PWSS (iii) CHILADANGI PWSS (iv) SAOTA PWSS (v) SHYAMPUR PWSS (vi) MAHISGHOT-(ZONE-I) PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000440/2024-2025 | 801/Arg | 23/08/2024 | 30/08/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0 | 0 | 100
Total | [13 empty] | 147.4 | 0 | 0