## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of SAOTA Piped Water Supply Scheme Under Pursura Block | SM/18962 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at PABA (1 NO.),BAIKUNTHAPUR (2Nos.),SAOTA (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer | Junior Engineer (Civill) | ORD/000645/2023-2024 | 3475/HUG | 29/11/2023 | 13/01/2024 | CIVIL CRAFT | 88.67 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | Source Augmentation of SAOTA Piped Water Supply Scheme Under Pursura Block | SM/18962 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of SAOTA Piped Water Supply Scheme Block- Pursura District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001291/2023-2024 | 4523/ED | 23/11/2023 | 21/02/2024 | TRIO CONCERN | 21.48 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of SAOTA Piped Water Supply Scheme Under Pursura Block | SM/18962 | Augmentation | Construction of 3 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 3 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 3 Nos. T.W & Distribution at BAIKUNTHAPUR (1Nos.), SAOTA (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) |  |  | ORD/000716/2023-2024 | 3352/HUG | 17/11/2023 | 16/01/2024 | A.R. CONSTRUCTION | 35.75 | 0 | 0 | 0
Total | [13 empty] | 145.89 | 0 | 0