## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Source Augmentation of SAOTA Piped Water Supply Scheme Under Pursura Block | SM/18962 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of SAOTA Piped Water Supply Scheme Block- Pursura District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001291/2023-2024 | 4523/ED | 23/11/2023 | 21/02/2024 | TRIO CONCERN | 21.48 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of SAOTA Piped Water Supply Scheme Under Pursura Block | SM/18962 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at PABA (1 NO.),BAIKUNTHAPUR (2Nos.),SAOTA (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer | Junior Engineer (Civill) | ORD/000645/2023-2024 | 3475/HUG | 29/11/2023 | 13/01/2024 | CIVIL CRAFT | 88.67 | 14.3 | 16.13 | 60
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of SAOTA Piped Water Supply Scheme Under Pursura Block | SM/18962 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of BHANGAMORA, SAOTA, PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000450/2024-2025 | 4081/HUG | 19/12/2024 | 19/03/2025 | R.K. TRADERS | 20.96 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Source Augmentation of SAOTA Piped Water Supply Scheme Under Pursura Block | SM/18962 | Augmentation | Construction of 3 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 3 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 3 Nos. T.W & Distribution at BAIKUNTHAPUR (1Nos.), SAOTA (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer | Junior Engineer (Civill) | ORD/000716/2023-2024 | 3352/HUG | 17/11/2023 | 03/01/2026 | A.R. CONSTRUCTION | 35.75 | 0 | 0 | 20
5 | HOOGHLY |  | Hooghly Division | Source Augmentation of SAOTA Piped Water Supply Scheme Under Pursura Block | SM/18962 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) PURBA KRISHNAPUR PWSS- 2no¿s, (2) GHARGHOHAL PWSS ¿ 2 no¿s, (3) SAOTA PWSS - 1no¿s, (4) SAIDPUR (Z-I) PWSS- 1no¿s, (5) SAIDPUR (Z-II)PWSS- 2no¿s, (6) SHYAMBALLAVPUR PWSS- 1no¿s, (7) KAKNAN PWSS- 1no¿s, (8) DIHIBATPUR PWSS(Z-II)- 1no¿s, (9) MAHISGHOT PWSS(Z-II) ¿ 2no¿s, (10) KANPUR PWSS - 1no¿s | Assistant Engineer | Junior Engineer (Civill) | ORD/002299/2024-2025 | 1157/Arg | 10/12/2024 | 10/01/2025 | M/S KHAMRUI CONSTRUCTION | 0.98 | 0 | 0 | 100
Total | [13 empty] | 167.84 | 14.3 | 8.52