## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of PABA Piped Water Supply Scheme under Goghat-II Block | SM/18963 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at PABA (1 NO.),BAIKUNTHAPUR (2Nos.),SAOTA (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer | Junior Engineer (Civill) | ORD/000645/2023-2024 | 3475/HUG | 29/11/2023 | 13/01/2024 | CIVIL CRAFT | 88.67 | 0 | 0 | 60
2 | HOOGHLY |  | Electrical | Source Augmentation of PABA Piped Water Supply Scheme under Goghat-II Block | SM/18963 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Paba water supply scheme, T.W. No. III, Block: Goghat-II, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/002575/2022-2023 | 2046/ED | 01/12/2022 | 01/03/2023 | M/S G P ENTERPRISE | 11.11 | 10.8 | 97.21 | 30
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of PABA Piped Water Supply Scheme under Goghat-II Block | SM/18963 | Augmentation | Connection of T.W. No. III with distribution, Construction of 5.4 x 3.65 m Pump Room with Sanitary arrangement and Boundary Wall at PABA Piped Water Supply Scheme under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000649/2023-2024 | 3482/HUG | 29/11/2023 | 28/01/2024 | DHIRENDRA ENGINEERING & CONSTRUCTION | 23.74 | 17.73 | 74.7 | 100
Total | [13 empty] | 123.52 | 28.53 | 23.1