## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of HARADITYA Piped Water Supply Scheme under Arambag Block | SM/18964 | Augmentation | Construction of 6 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos. T.W & Distribution at HARADITYA (2Nos.), GOURHATI (2Nos.), MAINAN (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer | Junior Engineer (Civill) | ORD/000597/2023-2024 | 3312/HUG | 10/11/2023 | 09/05/2025 | DILIP KUMAR GHOSH | 70.72 | 0 | 0 | 32
2 | HOOGHLY |  | Electrical | Source Augmentation of HARADITYA Piped Water Supply Scheme under Arambag Block | SM/18964 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of HARADITYA Piped Water Supply Scheme Block- Arambag District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001292/2023-2024 | 4524/ED | 23/11/2023 | 21/02/2024 | WIZARDTECH SOLUTION | 21.49 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of HARADITYA Piped Water Supply Scheme under Arambag Block | SM/18964 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at HARADITYA (2Nos.),GOURHATI (2Nos.),MAINAN (1No.)W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer | Junior Engineer (Civill) | ORD/000646/2023-2024 | 3476/HUG | 29/11/2023 | 13/01/2024 | SPG ENTERPRISES | 87.88 | 0 | 0 | 20
4 | HOOGHLY |  | Hooghly Division | Source Augmentation of HARADITYA Piped Water Supply Scheme under Arambag Block | SM/18964 | Augmentation | Route Survey for Augmentation of Haraditya Piped Water Supply Scheme under Arambagh Sub - Division of Hooghly Division, P.H.E. Dte. (Part-B) | Assistant Engineer |  | ORD/001222/2025-2026 | 654/Arg | 31/07/2025 | 31/08/2025 | APEX ENGINEERING | 0.95 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Source Augmentation of HARADITYA Piped Water Supply Scheme under Arambag Block | SM/18964 | Augmentation | Route Survey for Augmentation of Haraditya Piped Water Supply Scheme under Arambagh Sub - Division of Hooghly Division, P.H.E. Dte. (Part-C) | Assistant Engineer |  | ORD/001223/2025-2026 | 655/Arg | 31/07/2025 | 31/08/2025 | APEX ENGINEERING | 0.95 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Source Augmentation of HARADITYA Piped Water Supply Scheme under Arambag Block | SM/18964 | Augmentation | Preparation of CAD-GIS Drawing and Pipe Network Design for Augmentation of Haraditya Piped Water Supply Scheme under Arambagh Sub - Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001215/2025-2026 | 651/Arg | 31/07/2025 | 31/08/2025 | APEX ENGINEERING | 0.84 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | Source Augmentation of HARADITYA Piped Water Supply Scheme under Arambag Block | SM/18964 | Augmentation | Preparation of DPR for Augmentation of Haraditya Piped Water Supply Scheme under Arambagh Sub - Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001216/2025-2026 | 652/Arg | 31/07/2025 | 31/08/2025 | APEX ENGINEERING | 0.78 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | Source Augmentation of HARADITYA Piped Water Supply Scheme under Arambag Block | SM/18964 | Augmentation | Route Survey for Augmentation of Haraditya Piped Water Supply Scheme under Arambagh Sub - Division of Hooghly Division, P.H.E. Dte. (Part-A) | Assistant Engineer |  | ORD/001221/2025-2026 | 653/Arg | 31/07/2025 | 31/08/2025 | APEX ENGINEERING | 0.73 | 0 | 0 | 0
Total | [13 empty] | 184.34 | 0 | 0