## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca | SM/18966 | Augmentation | Sinking of 1(one) No Big dia tube well (250 mm X 150mm) with supply of PVC Pipe and strainer and having depth upto 150Mtr at 3rd TW site of Chikrand Zone-I W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000123/2022-2023 | 1273/HUG | 23/06/2022 | 23/07/2022 | M/S SYCHROTECH INDUSTRY | 8.2 | 0 | 0 | 98
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca | SM/18966 | Augmentation | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at CHIKRAND ZONE-I (1No.), CHIKRAND ZONE-II (1No.), CHANDITALA (2NOS.) W/S Scheme under Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000598/2023-2024 | 3313/HUG | 10/11/2023 | 04/01/2025 | S.D ENTERPRISE (SAMIR KR. DAS) | 47.18 | 11.75 | 24.9 | 40
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca | SM/18966 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at MAINAN(1No.),CHIKRAND ZONE-I (1No.),CHIKRAND ZONE-II (1No.) ,CHANDITALA (2NOS.) W/S Scheme under Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer,Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000622/2023-2024 | 3388/HUG | 22/11/2023 | 06/01/2024 | SPG ENTERPRISES | 87.88 | 14.26 | 16.23 | 100
4 | HOOGHLY |  | Electrical | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca | SM/18966 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme Block- Chanditala-II District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/001294/2023-2024 | 4526/ED | 23/11/2023 | 11/05/2026 | DEBJYOTI BASU | 10.75 | 10.46 | 97.38 | 90
5 | HOOGHLY |  | Hooghly Division | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca | SM/18966 | Augmentation | Laying Distribution of left out portion of pipeline to restore the water supply at Chikrand Jalapara & Bankagacha (part) and other allied works at Chikrand (Zone-I) Water Supply Scheme within Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000863/2023-2024 | 746/HUG | 05/03/2024 | 25/03/2024 | AMBIAN INFRASTRUCTURE | 23.36 | 9.41 | 40.27 | 50
6 | HOOGHLY |  | Hooghly Division | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca | SM/18966 | Augmentation | Laying Distribution of left out portion and Land Development at Chikrand Jalapara at Chikrand (Zone-I) Water Supply Scheme within Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000861/2023-2024 | 745/HUG | 05/03/2024 | 30/12/2024 | SADHUKHAN ENTERPRISE | 59.95 | 8.96 | 14.95 | 80
7 | HOOGHLY |  | Hooghly Division | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca | SM/18966 | Augmentation | Construction of Switch Room,Boundary wall,and rising main with interconnection at CHIKRAND W/s Scheme(Zone 1)Naity Baralpara,Chanditala-II Block under Hooghly Division PHE Dte.Source Augmentation. |  |  | ORD/000267/2024-2025 | 3614/HUG | 05/11/2024 | 04/01/2025 | S D ENTERPRISE | 25.82 | 0 | 0 | 0
8 | HOOGHLY |  | Electrical | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca | SM/18966 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHIKRAND MINI PIPED W/S SCHEME, Block: Chanditala-II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000395/2024-2025 | 1479/ED | 25/07/2024 | 23/10/2024 | SHIVAM ENTERPRISE | 7.58 | 0 | 0 | 0
9 | HOOGHLY |  | Electrical | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca | SM/18966 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHIKRAND PIPED W/S SCHEME, Zone - I, T.W. No. IV, Block: Chanditala - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000176/2024-2025 | 1200/ED | 14/06/2024 | 12/09/2024 | NITESH MANAGEMENT | 10.72 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca | SM/18966 | Augmentation | Sinking of Tubewell,Construction of Switch Room,Boundary wall,and rising main with interconnection at Danbatipur ,Chikrand W/s Scheme(Zone-1)Danbatipur , Naity; Chanditala-II Block underSerampore Sub-Division of Hooghly Division PHE Dte.. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000438/2024-2025 | 4042/HUG | 19/12/2024 | 20/06/2025 | M/S T.K.B. CONSTRUCTION | 47.79 | 0 | 0 | 25
11 | HOOGHLY |  | Hooghly Division | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca | SM/18966 | Augmentation | Laying Distribution of left out portion of pipeline at Chikrand Water Supply Scheme within Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000901/2023-2024 | 822/HUG | 11/03/2024 | 10/04/2024 | S D ENTERPRISE | 24.19 | 22.77 | 94.13 | 80
12 | HOOGHLY |  | Hooghly Division | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca | SM/18966 | Augmentation | Laying Distribution of left out portion of pipeline to restore the water supply at Chikrand (Zone-II) Water Supply Scheme within Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000894/2023-2024 | 818/HUG | 11/03/2024 | 01/11/2024 | KARALI MOHAN KHAMRUI | 20.13 | 0 | 0 | 80
13 | HOOGHLY |  | Hooghly Division | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca | SM/18966 | Augmentation | Designing making and erection of Display Board using logo and tag line of JalJeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Piarapur (P) village under Piarapur PWSS (2 nos.) 2. Baksa village under Baksa PWSS (2 nos.) 3. Naiti village under Chikrand PWSS (2 nos.) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001029/2023-2024 | 169/SER | 11/03/2024 | 18/03/2024 | JOY GURU ENTERPRISE | 0.95 | 0.95 | 100 | 80
14 | HOOGHLY |  | Hooghly Division | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca | SM/18966 | Augmentation | Construction of Boundary Wall at proposed Head work Site of Chikrand (Zone-I) W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000850/2023-2024 | 733/HUG | 05/03/2024 | 21/02/2025 | DIBYENDU DHARA | 24.04 | 3.11 | 12.95 | 40
15 | HOOGHLY |  | Electrical | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca | SM/18966 | Augmentation | Quotation money deposition for new service connection at Chikrand w/s scheme, Dist.-Hooghly under PHE Dte. Application No- 5004377254 Reference ID- 503729858 SM Code- 18966 |  |  | BILL/02275/2024-2025 | BP-24-25-584 | 19/11/2024 | 19/11/2024 | WBSEDCL | 5.2 | 0 | 0 | 0
16 | HOOGHLY |  | Hooghly Division | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca | SM/18966 | Augmentation | Emargency replacement of valves and allied works at Baksa & Chickrand Zone -I, II Water Supply Scheme under Serampore sub-division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001305/2024-2025 | 77/SER | 20/01/2025 | 30/01/2025 | JOY GURU ENTERPRISE | 4.28 | 2.19 | 51.14 | 90
17 | HOOGHLY |  | Hooghly Division | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca | SM/18966 | Augmentation | Cleaning of Chokage Pipeline and Replace of Damaged Ferrule at different mouzas of CHICKRAND W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001252/2024-2025 | 52/SER | 20/01/2025 | 27/01/2025 | TOTON MONDAL | 4.92 | 2.18 | 44.41 | 90
18 | HOOGHLY |  | Hooghly Division | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca | SM/18966 | Augmentation | Repairing of 2 nos. Pump House at Adan Shibtala (P.H. No.-II) of Chikrand (Zone-I) Water Supply Scheme and Pump House AND GODOWN at Chanditala (H/W Site) of Chanditala Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001308/2024-2025 | 80/SER | 20/01/2025 | 30/01/2025 | GHOSH ENTERPRISE | 4.7 | 0 | 0 | 90
19 | HOOGHLY |  | Hooghly Division | Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme by installing Two (2) nos. Tube Wells including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by loca | SM/18966 | Augmentation | Surging/Development of old tubewell using suitable air compressor to increase the yield at different Water Supply Scheme within Serampore Sub-Division of Hooghly Division, P.H.E. Dte. (Chickrand Z-II,Krishnarampur H/W,JangalparaH/W& 2nd TW,Radhanagar H/W & 2nd TW) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000017/2025-2026 | 288/SER | 17/04/2025 | 27/04/2025 | G. T. AGRO CENTRE | 4.1 | 0 | 0 | 90
Total | [13 empty] | 421.74 | 86.05 | 20.4