## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of CHIKRAND ZONE-II Piped Water Supply Scheme by installing One (1) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by local | SM/18967 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at MAINAN(1No.),CHIKRAND ZONE-I (1No.),CHIKRAND ZONE-II (1No.) ,CHANDITALA (2NOS.) W/S Scheme under Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer,Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000622/2023-2024 | 3388/HUG | 22/11/2023 | 06/01/2024 | SPG ENTERPRISES | 87.88 | 14.02 | 15.95 | 100
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of CHIKRAND ZONE-II Piped Water Supply Scheme by installing One (1) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by local | SM/18967 | Augmentation | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at CHIKRAND ZONE-I (1No.), CHIKRAND ZONE-II (1No.), CHANDITALA (2NOS.) W/S Scheme under Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000598/2023-2024 | 3313/HUG | 10/11/2023 | 04/01/2025 | S.D ENTERPRISE (SAMIR KR. DAS) | 47.18 | 7.08 | 15.01 | 40
3 | HOOGHLY |  | Electrical | Source Augmentation of CHIKRAND ZONE-II Piped Water Supply Scheme by installing One (1) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by local | SM/18967 | Augmentation | Quotation money deposition for new service connection at Chikrand w/s scheme, Dist.-Hooghly under PHE Dte. Application No- 5004485180 Reference ID- 503806101 SM Code- 18967 v |  |  | BILL/02480/2024-2025 | 615 | 04/12/2024 | 04/12/2024 | WBSEDCL | 10.74 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Source Augmentation of CHIKRAND ZONE-II Piped Water Supply Scheme by installing One (1) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC by local | SM/18967 | Augmentation | Laying Distribution of left out portion of pipeline to restore the water supply at Chikrand (Zone-II) Water Supply Scheme within Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000889/2023-2024 | 813/HUG | 11/03/2024 | 01/01/2025 | SAHA CONSTRUCTION AND CO | 63.24 | 17.81 | 28.17 | 90
Total | [13 empty] | 209.04 | 38.92 | 18.62