## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of BORHAL Piped Water Supply Scheme by installing new Two (2) Nos. Tube Wells including Connection with Distribution & other allied work to meet up the water demand under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | SM/18968 | Augmentation | Balance LDS and other allied works within left out habitation of various Mouzas in Borhal (Zone-II) W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000785/2023-2024 | 532/HUG | 20/02/2024 | 06/03/2024 | MA CONSTRUCTION | 16.06 | 0 | 0 | 80
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of BORHAL Piped Water Supply Scheme by installing new Two (2) Nos. Tube Wells including Connection with Distribution & other allied work to meet up the water demand under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | SM/18968 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Nikash village under Borhal PWSS (2 nos.) 2. Borhal under Borhal PWSS (2 nos.) 3. Satghara village under Borhal PWSS (2 nos.) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000964/2023-2024 | 175/SER | 11/03/2024 | 18/03/2024 | TOTON MONDAL | 0.95 | 0 | 0 | 80
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of BORHAL Piped Water Supply Scheme by installing new Two (2) Nos. Tube Wells including Connection with Distribution & other allied work to meet up the water demand under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | SM/18968 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Kumarbazar village under Antpur PWSS (2 nos.) 2. Paschim Durgapur village under Borhal PWSS (2 nos.) 3. Ilampur village under Borhal PWSS (2 nos.) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000960/2023-2024 | 172/SER | 11/03/2024 | 18/03/2024 | JOY GURU ENTERPRISE | 0.95 | 0 | 0 | 80
4 | HOOGHLY |  | Hooghly Division | Source Augmentation of BORHAL Piped Water Supply Scheme by installing new Two (2) Nos. Tube Wells including Connection with Distribution & other allied work to meet up the water demand under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | SM/18968 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Dakshin Dilakash village under Borhal PWSS (2 nos.) 2. Mandaran Dilakash village under Borhal PWSS (2 nos.) 3. Khurigachhi village under Borhal PWSS (2 nos.) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000962/2023-2024 | 173/SER | 11/03/2024 | 18/03/2024 | TOTON MONDAL | 0.95 | 0 | 0 | 80
5 | HOOGHLY |  | Hooghly Division | Source Augmentation of BORHAL Piped Water Supply Scheme by installing new Two (2) Nos. Tube Wells including Connection with Distribution & other allied work to meet up the water demand under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | SM/18968 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Kulakash village under Borhal PWSS (2 nos.) 2. Kandar Panagar village under Borhal PWSS (2 nos.) 3. Paschim Gobindapur village under Borhal PWSS (2 nos.) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000963/2023-2024 | 174/SER | 11/03/2024 | 18/03/2024 | TOTON MONDAL | 0.95 | 0 | 0 | 80
6 | HOOGHLY |  | Hooghly Division | Source Augmentation of BORHAL Piped Water Supply Scheme by installing new Two (2) Nos. Tube Wells including Connection with Distribution & other allied work to meet up the water demand under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | SM/18968 | Augmentation | Designing making and erection of Display Board using logo and tag line of JalJeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Mathurabati village under Borhal PWSS (2 nos.) 2. Masinan village under Radhanagar PWSS (2 nos.) 3. Kuliara village under Morhal PWSS (2 nos.) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000965/2023-2024 | 176/SER | 11/03/2024 | 18/03/2024 | JOY GURU ENTERPRISE | 0.95 | 0 | 0 | 80
7 | HOOGHLY |  | Electrical | Source Augmentation of BORHAL Piped Water Supply Scheme by installing new Two (2) Nos. Tube Wells including Connection with Distribution & other allied work to meet up the water demand under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | SM/18968 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of BORHAL Piped Water Supply Scheme Block- Jangipara District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/002466/2023-2024 | 327/ED | 21/02/2024 | 12/06/2026 | DEY ENTERPRISE | 20.85 | 0 | 0 | 45
Total | [13 empty] | 41.68 | 0 | 0