## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18969 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at CHAPTA (2Nos.), SOMRA (2Nos.), NAMAJGRAM (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000611/2023-2024 | 3360/HUG | 21/11/2023 | 05/01/2024 | AUXILIARY TUBEWELL DRILLERS | 87.88 | 0 | 0 | 40
2 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18969 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in Somara-I GP of Balagrah Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000920/2023-2024 | 240/CH | 12/03/2024 | 11/04/2024 | MAA BUNAMATA ENTERPRISE | 4.98 | 0 | 0 | 70
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18969 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in Somara-II GP of Balagrah Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000921/2023-2024 | 241/CH | 12/03/2024 | 11/04/2024 | ASHA ENTERPRISE | 4.98 | 0 | 0 | 50
4 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18969 | Augmentation | Quotation for new service connection for source Augmentation of SOMRA Water Supply Scheme, PH NO- IV in the district Hooghly under Electrical Division,PHE Dte. ( SM/18969), Reference Id- 503814868 Application no- 5004498035 |  |  | BILL/02601/2024-2025 | 630 | 18/12/2024 | 18/12/2024 | WBSEDCL | 8.62 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18969 | Augmentation | Quotation for new service connection for source Augmentation of SOMRA Water Supply Scheme, PH NO- III in the district Hooghly under Electrical Division,PHE Dte. ( SM/18969), Reference Id- 503814816 Application no- 5004497772 |  |  | BILL/02602/2024-2025 | 629 | 18/12/2024 | 18/12/2024 | WBSEDCL | 8.47 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18969 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at CHAPTA (2Nos.), SOMRA (2Nos.), NAMAJGRAM (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000579/2023-2024 | 3237/HUG | 06/11/2023 | 30/07/2025 | M/S T.K.B. CONSTRUCTION | 59.02 | 0 | 0 | 60
7 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18969 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/001214/2023-2024 | 4492/ED | 23/11/2023 | 02/11/2025 | MAA TARA CONSTRUCTION | 21.47 | 0 | 0 | 50
Total | [13 empty] | 195.44 | 0 | 0