## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18969 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at CHAPTA (2Nos.), SOMRA (2Nos.), NAMAJGRAM (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) |  | ORD/000579/2023-2024 | 3237/HUG | 06/11/2023 | 05/01/2024 | M/S T.K.B. CONSTRUCTION | 59.02 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18969 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001214/2023-2024 | 4492/ED | 23/11/2023 | 21/02/2024 | MAA TARA CONSTRUCTION | 21.47 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18969 | Augmentation | 8TH Continuation of Deployment of 4(four) nos. Security Guard without arm for Guarding Arrangement of office cum Store at SOMRA W/S Scheme under Chinsurah Sub-Division, under Hooghly Division, P.H.E Dte. Period 1 month from 01.01.2024 to 31.01.2024 | Assistant Engineer (Civil) |  | ORD/000817/2023-2024 | 1144/CH | 27/12/2023 | 27/01/2024 | P. B. ENTERPRISE(PINTU BHADURI) | 0.87 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18969 | Augmentation | 9TH Continuation of Deployment of 4(four) nos. Security Guard without arm for Guarding Arrangement of office cum Store at SOMRA W/S Scheme under Chinsurah Sub-Division, under Hooghly Division, P.H.E Dte. Period 1 month from 01.02.2024 to 29.02.2024 | Assistant Engineer (Civil) |  | ORD/001025/2023-2024 | 81/CH | 29/01/2024 | 27/02/2024 | P. B. ENTERPRISE(PINTU BHADURI) | 0.81 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18969 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in Somara-II GP of Balagrah Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000921/2023-2024 | 241/CH | 12/03/2024 | 11/04/2024 | ASHA ENTERPRISE | 4.98 | 2.38 | 47.85 | 50
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18969 | Augmentation | Construction of Store room for temporary Chlorine and maintenance material storage For Balagarh Block under Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/001037/2023-2024 | 279/CH | 14/03/2024 | 21/03/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18969 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at CHAPTA (2Nos.), SOMRA (2Nos.), NAMAJGRAM (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000611/2023-2024 | 3360/HUG | 21/11/2023 | 05/01/2024 | AUXILIARY TUBEWELL DRILLERS | 87.88 | 14.66 | 16.68 | 40
8 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18969 | Augmentation | 11TH Continuation Deployment of 4(four) nos. Security Guard without arm for Guarding Arrangement of office cum Store at SOMRA W/S Scheme under Chinsurah Sub-Division, under Hooghly Division, P.H.E Dte. Period 1 month from 01.04.2024 to 30.04.2024. | Assistant Engineer (Civil) |  | ORD/001434/2023-2024 | 369/CH | 28/03/2024 | 27/04/2024 | P. B. ENTERPRISE(PINTU BHADURI) | 0.84 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18969 | Augmentation | 10th Continuation Deployment of 4(four) nos. Security Guard without arm for Guarding Arrangement of office cum Store at SOMRA W/S Scheme under Chinsurah Sub-Division, under Hooghly Division, P.H.E Dte. Period 1 month from 01.03.2024 to 31.03.2024. | Assistant Engineer (Civil) |  | ORD/001432/2023-2024 | 187/CH | 29/02/2024 | 31/03/2024 | P. B. ENTERPRISE(PINTU BHADURI) | 0.87 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18969 | Augmentation | 13TH Continuation Deployment of 4(four) nos. Security Guard without arm for Guarding Arrangement of office cum Store at SOMRA W/S Scheme under Chinsurah Sub-Division, under Hooghly Division, P.H.E Dte. Period 1 month from 01.06.2024 to 30.06.2024. | Assistant Engineer (Civil) |  | ORD/000069/2024-2025 | 487/CH | 30/05/2024 | 29/06/2024 | P. B. ENTERPRISE(PINTU BHADURI) | 0.84 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18969 | Augmentation | 12TH Continuation Deployment of 4(four) nos. Security Guard without arm for Guarding Arrangement of office cum Store at SOMRA W/S Scheme under Chinsurah Sub-Division, under Hooghly Division, P.H.E Dte. Period 1 month from 01.05.2024 to 31.05.2024 | Assistant Engineer (Civil) |  | ORD/000067/2024-2025 | 417/CH | 29/04/2024 | 30/05/2024 | P. B. ENTERPRISE(PINTU BHADURI) | 0.87 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18969 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in Somara-I GP of Balagrah Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000920/2023-2024 | 240/CH | 12/03/2024 | 11/04/2024 | MAA BUNAMATA ENTERPRISE | 4.98 | 3 | 60.29 | 70
13 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18969 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in BATIKA-BAINCHI GP of PANDUA Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000922/2023-2024 | 242/CH | 12/03/2024 | 11/04/2024 | RAJMAHAL ENTERPRISE | 4.99 | 0 | 0 | 85
14 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18969 | Augmentation | 15TH Continuation Deployment of 4(four) nos. Security Guard without arm for Guarding Arrangement of office cum Store at SOMRA W/S Scheme under Chinsurah Sub-Division, under Hooghly Division, P.H.E Dte. Period 1 month from 01.08.2024 to 31.08.2024 | Assistant Engineer (Civil) |  | ORD/000177/2024-2025 | 669/CH | 29/07/2024 | 29/08/2024 | P. B. ENTERPRISE(PINTU BHADURI) | 0.87 | 0 | 0 | 0
Total | [13 empty] | 190.24 | 20.05 | 10.54