## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18970 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at CHAPTA (2Nos.), SOMRA (2Nos.), NAMAJGRAM (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000579/2023-2024 | 3237/HUG | 06/11/2023 | 30/07/2025 | M/S T.K.B. CONSTRUCTION | 59.02 | 0 | 0 | 60
2 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18970 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at NAMAJGRAM (1No.), RAMESWARPUR (2Nos.), KAMARPARA (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer (Civil) |  | ORD/000580/2023-2024 | 3238/HUG | 06/11/2023 | 05/01/2024 | NIGAM CONSTRUCTION | 59.08 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18970 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at NAMAJGRAM (1No.), RAMESWARPUR (2Nos.), KAMARPARA (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000616/2023-2024 | 3361/HUG | 21/11/2023 | 05/01/2024 | RAJU CONSTRUCTION | 87.09 | 0 | 0 | 75
4 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18970 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001243/2023-2024 | 4493/ED | 23/11/2023 | 21/02/2024 | M.S. ENTERPRISE | 21.51 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18970 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at CHAPTA (2Nos.), SOMRA (2Nos.), NAMAJGRAM (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000611/2023-2024 | 3360/HUG | 21/11/2023 | 05/01/2024 | AUXILIARY TUBEWELL DRILLERS | 87.88 | 13.22 | 15.05 | 40
6 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18970 | Augmentation | Quotation for new service connection for source Augmentation of NAMAJGRAM Water Supply Scheme, TW NO- IV in the district Hooghly under Electrical Division, PHE Dte. ( SM/18970), Reference Id- 503802582 Application no- 5004479726 |  |  | BILL/02527/2024-2025 | 602 | 05/12/2024 | 05/12/2024 | WBSEDCL | 19.9 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18970 | Augmentation | Quotation for new service connection for source Augmentation of NAMAJGRAM Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. ( SM/18970), Reference Id- 503802583 Application no- 5004479665 |  |  | BILL/02528/2024-2025 | 612 | 05/12/2024 | 05/12/2024 | WBSEDCL | 4.24 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18970 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Namajgram PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) |  | ORD/001952/2024-2025 | 274/CH | 20/02/2025 | 02/03/2025 | GHOSH CONSTRUCTION | 2.58 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18970 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at H/W Site of Namajgram PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) |  | ORD/001915/2024-2025 | 266/CH | 20/02/2025 | 02/03/2025 | GHOSH CONSTRUCTION | 4.53 | 0 | 0 | 0
Total | [13 empty] | 345.84 | 13.22 | 3.82