## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF RAMESWARPUR PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18971 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at NAMAJGRAM (1No.), RAMESWARPUR (2Nos.), KAMARPARA (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer (Civil) |  | ORD/000580/2023-2024 | 3238/HUG | 06/11/2023 | 05/01/2024 | NIGAM CONSTRUCTION | 59.08 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF RAMESWARPUR PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18971 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at NAMAJGRAM (1No.), RAMESWARPUR (2Nos.), KAMARPARA (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000616/2023-2024 | 3361/HUG | 21/11/2023 | 05/01/2024 | RAJU CONSTRUCTION | 87.09 | 14.22 | 16.32 | 75
3 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF RAMESWARPUR PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18971 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF RAMESWARPUR PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001244/2023-2024 | 4494/ED | 23/11/2023 | 21/02/2024 | R.K.ENTERPRISE | 21.48 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF RAMESWARPUR PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18971 | Augmentation | Quotation for new service connection for source Augmentation of Rameswarpur Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. ( SM/18971), Reference Id- 503733787 Application no- 5004386169 |  |  | BILL/01969/2024-2025 | 479 | 01/10/2024 | 01/10/2024 | WBSEDCL | 4.53 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF RAMESWARPUR PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18971 | Augmentation | Quotation for new service connection for source Augmentation of Rameswarpur Water Supply Scheme, TW NO- IV in the district Hooghly under Electrical Division, PHE Dte. (SM/18971), Reference Id- 503726898 Application no- 5004370950 |  |  | BILL/01970/2024-2025 | 481 | 01/10/2024 | 01/10/2024 | WBSEDCL | 4.15 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF RAMESWARPUR PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18971 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Rameswarpur PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) |  | ORD/001919/2024-2025 | 270/CH | 20/02/2025 | 02/03/2025 | SAMRAT CONSTRUCTION | 2.68 | 0 | 0 | 0
Total | [13 empty] | 179.02 | 14.22 | 7.94