## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BHABANIPUR CHAR PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18973 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF BHABANIPUR CHAR PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001246/2023-2024 | 4496/ED | 23/11/2023 | 21/02/2024 | PERPETUAL ENTERPRISE | 21.7 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BHABANIPUR CHAR PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18973 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BHABANIPUR CHAR (2Nos.), JAYRAMBATI (2Nos.), DEBANANDAPUR (1 No.)W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000623/2023-2024 | 3389/HUG | 22/11/2023 | 06/01/2024 | AUXILIARY TUBEWELL DRILLERS | 87.88 | 0 | 0 | 30
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BHABANIPUR CHAR PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18973 | Augmentation | Replacement of damaged AC pipe line with HDPE pipeline and Shifting House Connection from existing main to new main at Khayramari Char of Bhawanipur Piped Water Supply Scheme under Chinusrah-Magra Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000034/2024-2025 | 536/CH | 14/06/2024 | 21/06/2024 | MAA BUNAMATA ENTERPRISE | 2.51 | 0 | 0 | 90
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BHABANIPUR CHAR PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18973 | Augmentation | Repairing & Renovation of Boundary Wall and Land Development At Head Works Site of Bhabanipur Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001963/2024-2025 | 285/CH | 20/02/2025 | 02/03/2025 | MAA BUNAMATA ENTERPRISE | 3.85 | 0 | 0 | 100
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BHABANIPUR CHAR PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18973 | Augmentation | Repairing & Renovation of Boundary Wall, Switch Room and Land Development At PH-II Site of Bhabanipur Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/002015/2024-2025 | 303/CH | 20/02/2025 | 02/03/2025 | SWARNA ENTERPRISE | 2.15 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BHABANIPUR CHAR PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18973 | Augmentation | Repairing & Renovation of Boundary Wall extensions, Switch Room & IP Room At Head Works Site of Bhabanipur Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002009/2024-2025 | 295/CH | 20/02/2025 | 02/03/2025 | MAA BUNAMATA ENTERPRISE | 4.49 | 0 | 0 | 100
Total | [13 empty] | 122.57 | 0 | 0