## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF JAYRAMBATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18974 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF JAYRAMBATI PIPED W/S SCHEME Block- Dhaniakhali District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001247/2023-2024 | 4497/ED | 23/11/2023 | 21/02/2024 | BISALAXMI ENTERPRISE | 21.48 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF JAYRAMBATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18974 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BHABANIPUR CHAR (2Nos.), JAYRAMBATI (2Nos.), DEBANANDAPUR (1 No.)W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000623/2023-2024 | 3389/HUG | 22/11/2023 | 06/01/2024 | AUXILIARY TUBEWELL DRILLERS | 87.88 | 27.43 | 31.21 | 30
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF JAYRAMBATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18974 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at DHAMAITIKAR (2Nos.), JAYRAMBATI (2 Nos.), DEPARA (1 Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) |  | ORD/000688/2023-2024 | 3725/HUG | 18/12/2023 | 16/02/2024 | BIMAL KUMAR HALDER | 59.73 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF JAYRAMBATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18974 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in SOMASPUR I GP of DHANIAKHALI Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000915/2023-2024 | 250/CH | 12/03/2024 | 11/04/2024 | SRI KRISHNA ENTERPRISE | 4.99 | 3.29 | 66.04 | 70
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF JAYRAMBATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18974 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in SOMASPUR II GP of DHANIAKHALI Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000916/2023-2024 | 251/CH | 12/03/2024 | 11/04/2024 | JOY GURU ENTERPRISE | 4.99 | 1.31 | 26.24 | 100
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF JAYRAMBATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18974 | Augmentation | REPAIRING & RENOVATION OF SWITCH ROOM INCLUDING BOUNDARY WALL AT 2ND TW SITE OF JAYRAMBATI WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURAH SUB-DIVISION UNDER HOOGHLY DIVISION, PHE DTE. | Assistant Engineer (Civil) |  | ORD/001841/2024-2025 | 218/CH | 19/02/2025 | 21/03/2025 | RAJMAHAL ENTERPRISE | 3.25 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF JAYRAMBATI PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18974 | Augmentation | REPAIRING & RENOVATION OF SWITCH ROOM INCLUDING BOUNDARY WALL AT HEAD WORKS SITE OF JAYRAMBATI WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURAH SUB DIVISION UNDER HOOGHLY DIVISION, PHE DTE. | Assistant Engineer (Civil) |  | ORD/001462/2024-2025 | 125/CH | 29/01/2025 | 08/02/2025 | RAJMAHAL ENTERPRISE | 4.85 | 0 | 0 | 0
Total | [13 empty] | 187.17 | 32.03 | 17.11