## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/18975 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at NATAGARI (2Nos.), MANDARAN (2Nos.), DEBANANDAPUR (1No.)W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000581/2023-2024 | 3239/HUG | 06/11/2023 | 05/01/2024 | RAJ AGRO SERVICE CENTRE | 59.62 | 0 | 0 | 20
2 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/18975 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME Block- ChinsurahMogra District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001249/2023-2024 | 4498/ED | 23/11/2023 | 21/02/2024 | R.N.S. TRADING | 22.03 | 0 | 0 | 40
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/18975 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BHABANIPUR CHAR (2Nos.), JAYRAMBATI (2Nos.), DEBANANDAPUR (1 No.)W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000623/2023-2024 | 3389/HUG | 22/11/2023 | 06/01/2024 | AUXILIARY TUBEWELL DRILLERS | 87.88 | 0 | 0 | 30
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/18975 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. 1. Debanandapur PWSS 2. Digsui Heora Z-I PWSS 3. Digsui Heora Z-II PWSS 4. Keota PWSS 5. Saptagram PWSS 6. Chanparui PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000820/2023-2024 | 198/CH | 29/02/2024 | 07/03/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0 | 0 | 50
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/18975 | Augmentation | Reparing & Washing of Existing Ferrule and Laying of HDPE Pipeline From existing Distribution System for providing FHTC of Debanandapur W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000770/2023-2024 | 127/CH | 16/02/2024 | 02/03/2024 | BIMAL KUMAR HALDER | 2.16 | 0 | 0 | 45
6 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/18975 | Augmentation | Quotation for the new service connection at Debanandapur (Source Aug.) [SM/18975] W/S Sch. T/W No. - II, (Manaspur near Lalbaba Ashram ) Block- - Chinsura-Mogra, Hooghly under BANDEL CCC, WBSEDCL, Application No. - 5004045960, Reference No. - 503581923 |  |  | BILL/06238/2023-2024 | 840 | 04/03/2024 | 04/03/2024 | WBSEDCL | 20.45 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/18975 | Augmentation | Quotation for the new service connection at Debanandapur (Source Aug.) [SM/18975] W/S Sch. T/W No. - I, (Near Sarat Library ) Block- - Chinsura-Mogra, Hooghly under BANDEL CCC, WBSEDCL, Application No. - 5004045949, Reference No. - 503581960 |  |  | BILL/06237/2023-2024 | 836 | 04/03/2024 | 04/03/2024 | WBSEDCL | 3.7 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/18975 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at NATAGARI (2Nos.), MANDARAN (2Nos.), DEBANANDAPUR (1No.)W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000617/2023-2024 | 3383/HUG | 22/11/2023 | 10/08/2025 | OSMAN SEKH | 87.84 | 0 | 0 | 20
9 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/18975 | Augmentation | Repairing & Renovation of Switch room and Store room at H/W Site of Debanandapur Z-I Water Supply Scheme Under Chinsurah Magra Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002011/2024-2025 | 297/CH | 20/02/2025 | 02/03/2025 | BIMAL KUMAR HALDER | 3.41 | 0 | 0 | 100
10 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/18975 | Augmentation | Repairing & Renovation of boundary wall and Land development at H/W Site of Debanandapur Z-I Water Supply Scheme Under Chinsurah Magra Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002013/2024-2025 | 301/CH | 20/02/2025 | 02/03/2025 | BIMAL KUMAR HALDER | 2.58 | 0 | 0 | 100
11 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/18975 | Augmentation | Laying C.I/D.I & HDPE pipes & specials for rising main & interconnection of Tube well No. 7 & Distribution line at Lal Baba Asram of Debanandapur W/S under Chinsurah Sub - Division P.H.E. Dte. |  |  | ORD/000857/2025-2026 | 2833/HUG | 17/11/2025 | 16/01/2026 | BIMAL KUMAR HALDER | 15.19 | 0 | 0 | 0
Total | [13 empty] | 305.82 | 0 | 0