## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF NATAGARI PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18976 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF NATAGARI PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001250/2023-2024 | 4499/ED | 23/11/2023 | 21/02/2024 | R.M.D TRADING. | 22.05 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF NATAGARI PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18976 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at NATAGARI (2Nos.), MANDARAN (2Nos.), DEBANANDAPUR (1No.)W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000581/2023-2024 | 3239/HUG | 06/11/2023 | 05/01/2024 | RAJ AGRO SERVICE CENTRE | 59.62 | 0 | 0 | 20
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF NATAGARI PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18976 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte. 1. Natagarh PWSS 2. Natunchar Krishnabati PWSS 3. Somra PWSS 4. Sripur Balagarh PWSS 5. Amodghata PWSS 6. Dharampur PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000819/2023-2024 | 197/CH | 29/02/2024 | 07/03/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0.95 | 100 | 50
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF NATAGARI PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18976 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at NATAGARI (2Nos.), MANDARAN (2Nos.), DEBANANDAPUR (1No.)W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000617/2023-2024 | 3383/HUG | 22/11/2023 | 10/08/2025 | OSMAN SEKH | 87.84 | 0 | 0 | 20
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF NATAGARI PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18976 | Augmentation | Repairing & Renovation of Switch Room and Store Room at H/W Site of Natagari Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/002004/2024-2025 | 288/CH | 20/02/2025 | 02/03/2025 | SOMNATH ADHYA | 3.42 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF NATAGARI PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18976 | Augmentation | Repairing & Renovation of boundary wall and Land development at H/W Site of Natagari Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/002003/2024-2025 | 287/CH | 20/02/2025 | 02/03/2025 | SOMNATH ADHYA | 3.03 | 0 | 0 | 0
Total | [13 empty] | 176.9 | 0.95 | 0.54