## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DHAMAITIKAR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18978 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF DHAMAITIKAR PIPED W/S SCHEME Block- Dhaniakhali District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/001252/2023-2024 | 4501/ED | 23/11/2023 | 01/10/2025 | S.G.-ENTERPRISE | 21.5 | 0 | 0 | 45
2 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DHAMAITIKAR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18978 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at DHAMAITIKAR (2Nos.), GUPTIPARA (1No.), ABDULPUR (1 No.), DEPARA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000618/2023-2024 | 3385/HUG | 22/11/2023 | 11/08/2025 | OSMAN SEKH | 87.83 | 34.59 | 39.38 | 40
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DHAMAITIKAR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18978 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at DHAMAITIKAR (2Nos.), JAYRAMBATI (2 Nos.), DEPARA (1 Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) |  | ORD/000688/2023-2024 | 3725/HUG | 18/12/2023 | 16/02/2024 | BIMAL KUMAR HALDER | 59.73 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DHAMAITIKAR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18978 | Augmentation | REPAIRING & RENOVATION OF SWITCH ROOM INCLUDING BOUNDARY WALL AT HEAD WORKS SITE OF DHAMAITIKAR WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURAH SUB-DIVISION UNDER HOOGHLY DIVISION, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001842/2024-2025 | 219/CH | 19/02/2025 | 21/03/2025 | R.K. TRADERS | 4.83 | 0 | 0 | 60
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DHAMAITIKAR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18978 | Augmentation | REPAIRING & RENOVATION OF SWITCH ROOM INCLUDING BOUNDARY WALL AT 2ND TW SITE OF DHAMAITIKAR WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURAH SUB-DIVISION UNDER HOOGHLY DIVISION, PHE DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001465/2024-2025 | 129/CH | 29/01/2025 | 08/02/2025 | R.K. TRADERS | 3.26 | 0 | 0 | 80
6 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DHAMAITIKAR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18978 | Augmentation | Electric quot. of WBSEDCL for New service Connection of Dhamaitikar T/W-III W/S scheme under Electrical Division PHE Dte. (SM/18978) |  |  | BILL/02827/2024-2025 | 652 | 09/01/2025 | 09/01/2025 | WBSEDCL | 10.6 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DHAMAITIKAR PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/18978 | Augmentation | Electric quot. of WBSEDCL for New service Connection of Dhamaitikar T/W-IV W/S scheme under Electrical Division PHE Dte. (SM/18978) |  |  | BILL/02831/2024-2025 | 653 | 09/01/2025 | 09/01/2025 | WBSEDCL | 12.06 | 0 | 0 | 0
Total | [13 empty] | 199.81 | 34.59 | 17.31