## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF GUPTIPARA PIPED W/S SCHEME UNDER BALAGAH BLOCK | SM/18979 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at DHAMAITIKAR (2Nos.), GUPTIPARA (1No.), ABDULPUR (1 No.), DEPARA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000618/2023-2024 | 3385/HUG | 22/11/2023 | 06/01/2024 | OSMAN SEKH | 87.83 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF GUPTIPARA PIPED W/S SCHEME UNDER BALAGAH BLOCK | SM/18979 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF GUPTIPARA PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001253/2023-2024 | 4502/ED | 23/11/2023 | 21/02/2024 | DIPA CHHETRI | 11.05 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF GUPTIPARA PIPED W/S SCHEME UNDER BALAGAH BLOCK | SM/18979 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at DHAMAITIKAR (2Nos.), GUPTIPARA (1No.), ABDULPUR (1 No.), DEPARA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) |  | ORD/000688/2023-2024 | 3725/HUG | 18/12/2023 | 16/02/2024 | BIMAL KUMAR HALDER | 59.73 | 0 | 0 | 0
Total | [13 empty] | 158.61 | 0 | 0