## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DEPARA PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18981 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF DEPARA PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001258/2023-2024 | 4504/ED | 23/11/2023 | 21/02/2024 | GOENKA ENTERPRISE | 10.75 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DEPARA PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18981 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at DHAMAITIKAR (2Nos.), GUPTIPARA (1No.), ABDULPUR (1 No.), DEPARA (1 No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000618/2023-2024 | 3385/HUG | 22/11/2023 | 11/08/2025 | OSMAN SEKH | 87.83 | 0 | 0 | 40
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DEPARA PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18981 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos.Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at DHAMAITIKAR (2Nos.), JAYRAMBATI (2 Nos.), DEPARA (1 Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) |  | ORD/000688/2023-2024 | 3725/HUG | 18/12/2023 | 16/02/2024 | BIMAL KUMAR HALDER | 59.73 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DEPARA PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18981 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at H/W Site of Depara PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) |  | ORD/001879/2024-2025 | 243/CH | 19/02/2025 | 01/03/2025 | SAMRAT CONSTRUCTION | 4.08 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF DEPARA PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18981 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Depara PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) |  | ORD/001912/2024-2025 | 263/CH | 20/02/2025 | 02/03/2025 | SAMRAT CONSTRUCTION | 2.75 | 0 | 0 | 0
6 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF DEPARA PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18981 | Augmentation | Quotation for new service connection for source Augmentation of DEPARA Water Supply Scheme, TW NO-III in the district Hooghly under Electrical Division,PHEDte. ( SM/18981), Reference Id- 503936087 Application no- 5004680010 |  |  | BILL/00292/2025-2026 | 42151 | 30/07/2025 | 30/07/2025 | WBSEDCL | 9.56 | 0 | 0 | 0
Total | [13 empty] | 174.69 | 0 | 0