## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Arambag | Hooghly Division | 'GROUND WATER BASED GHAR GOHAL PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' | SM/19013 | New | Material Requisition To Resource Division |  |  | RTOR000426/2023-2024 | 3057/38/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 3.29 | 0 | 0 | 0
2 | HOOGHLY | Arambag | Electrical | 'GROUND WATER BASED GHAR GOHAL PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' | SM/19013 | New | Quotation of New Service Connection for Ghar Gohal w/s scheme, PH No-II Block-Arambag, Dist-Hooghly under Electrical Division, PHE Dte.(SM/19013) Application No-5004282784 Reference Id-503686105 |  |  | BILL/01153/2024-2025 | 286 | 09/07/2024 | 09/07/2024 | WBSEDCL | 6.42 | 0 | 0 | 0
3 | HOOGHLY | Arambag | Electrical | 'GROUND WATER BASED GHAR GOHAL PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' | SM/19013 | New | Quotation of New Service Connection for Ghar Gohal w/s scheme, PH No-I Block-Arambag, Dist-Hooghly under Electrical Division, PHE Dte.(SM/19013) Application No-5004282705 Reference Id-503686110 |  |  | BILL/01152/2024-2025 | 285 | 09/07/2024 | 09/07/2024 | WBSEDCL | 5.39 | 0 | 0 | 0
4 | HOOGHLY | Arambag | Hooghly Division | 'GROUND WATER BASED GHAR GOHAL PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' | SM/19013 | New | GHAR GOHAL Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-rooms & boundary walls at different TW site under ARAMBAGH SUB-DIVISION Block-ARAMBAGH, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000273/2023-2024 | 3183/HUG | 30/10/2023 | 19/10/2025 | DAS TRADING | 194.07 | 0 | 0 | 30
5 | HOOGHLY | Arambag | Electrical | 'GROUND WATER BASED GHAR GOHAL PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' | SM/19013 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghar Gohal water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/001984/2023-2024 | 116/ED | 15/01/2024 | 29/06/2025 | GLACIER ENGINEERING CO. | 21.1 | 0 | 0 | 30
6 | HOOGHLY | Arambag | Electrical | 'GROUND WATER BASED GHAR GOHAL PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' | SM/19013 | New | Hiring of Luxury Car / Ambassadar (BS-IV) for Officical use of the Assistant Chief Engineer (M/E), PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000284/2024-2025 | 2870/HMSD | 04/06/2024 | 03/12/2024 | BHOLA DEY | 0.86 | 0 | 0 | 0
Total | [13 empty] | 231.15 | 0 | 0