## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Arambag | Hooghly Division | 'GROUND WATER BASED GHAR GOHAL PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' | SM/19013 | New | Material Requisition To Resource Division |  |  | RTOR000426/2023-2024 | 3057/38/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 3.29 | 0 | 0 | 0
2 | HOOGHLY | Arambag | Electrical | 'GROUND WATER BASED GHAR GOHAL PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' | SM/19013 | New | Quotation of New Service Connection for Ghar Gohal w/s scheme, PH No-II Block-Arambag, Dist-Hooghly under Electrical Division, PHE Dte.(SM/19013) Application No-5004282784 Reference Id-503686105 |  |  | BILL/01153/2024-2025 | 286 | 09/07/2024 | 09/07/2024 | WBSEDCL | 6.42 | 0 | 0 | 0
3 | HOOGHLY | Arambag | Electrical | 'GROUND WATER BASED GHAR GOHAL PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' | SM/19013 | New | Quotation of New Service Connection for Ghar Gohal w/s scheme, PH No-I Block-Arambag, Dist-Hooghly under Electrical Division, PHE Dte.(SM/19013) Application No-5004282705 Reference Id-503686110 |  |  | BILL/01152/2024-2025 | 285 | 09/07/2024 | 09/07/2024 | WBSEDCL | 5.39 | 0 | 0 | 0
4 | HOOGHLY | Arambag | Hooghly Division | 'GROUND WATER BASED GHAR GOHAL PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' | SM/19013 | New | GHAR GOHAL Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-rooms & boundary walls at different TW site under ARAMBAGH SUB-DIVISION Block-ARAMBAGH, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000273/2023-2024 | 3183/HUG | 30/10/2023 | 19/10/2025 | DAS TRADING | 194.07 | 109.72 | 56.53 | 30
5 | HOOGHLY | Arambag | Electrical | 'GROUND WATER BASED GHAR GOHAL PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' | SM/19013 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghar Gohal water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/001984/2023-2024 | 116/ED | 15/01/2024 | 29/06/2025 | GLACIER ENGINEERING CO. | 21.1 | 0 | 0 | 30
6 | HOOGHLY | Arambag | Electrical | 'GROUND WATER BASED GHAR GOHAL PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' | SM/19013 | New | Hiring of Luxury Car / Ambassadar (BS-IV) for Officical use of the Assistant Chief Engineer (M/E), PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000284/2024-2025 | 2870/HMSD | 04/06/2024 | 03/12/2024 | BHOLA DEY | 0.86 | 0 | 0 | 0
7 | HOOGHLY | Arambag | Hooghly Division | 'GROUND WATER BASED GHAR GOHAL PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' | SM/19013 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) PURBA KRISHNAPUR PWSS- 2no¿s, (2) GHARGHOHAL PWSS ¿ 2 no¿s, (3) SAOTA PWSS - 1no¿s, (4) SAIDPUR (Z-I) PWSS- 1no¿s, (5) SAIDPUR (Z-II)PWSS- 2no¿s, (6) SHYAMBALLAVPUR PWSS- 1no¿s, (7) KAKNAN PWSS- 1no¿s, (8) DIHIBATPUR PWSS(Z-II)- 1no¿s, (9) MAHISGHOT PWSS(Z-II) ¿ 2no¿s, (10) KANPUR PWSS - 1no¿s | Assistant Engineer | Junior Engineer (Civill) | ORD/002299/2024-2025 | 1157/Arg | 10/12/2024 | 10/01/2025 | M/S KHAMRUI CONSTRUCTION | 0.98 | 0 | 0 | 100
Total | [13 empty] | 232.12 | 109.72 | 47.27