## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Arambag | Hooghly Division | Bhalia (Zone-II) Piped Water Supply Scheme, Block- Arambagh, District-Hooghly | SM/19014 | New | Material Requisition To Resource Division |  |  | RTOR000448/2023-2024 | 3057/25/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 2.06 | 0 | 0 | 0
2 | HOOGHLY | Arambag | Electrical | Bhalia (Zone-II) Piped Water Supply Scheme, Block- Arambagh, District-Hooghly | SM/19014 | New | Quotation of New Service Connection for Bhalia w/s Scheme,Zone-II,PH No-I Block-Arambag,Dist-Hooghly under Electrical Division,PHE Dte.(SM/19014) Application No-5004416386 Reference Id-503753715 |  |  | BILL/01983/2024-2025 | 478 | 01/10/2024 | 01/10/2024 | WBSEDCL | 6.49 | 0 | 0 | 0
3 | HOOGHLY | Arambag | Hooghly Division | Bhalia (Zone-II) Piped Water Supply Scheme, Block- Arambagh, District-Hooghly | SM/19014 | New | BHALIA ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site, under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Block Arambagh, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000552/2023-2024 | 3181/HUG | 30/10/2023 | 31/03/2025 | TANISA ENTERPRISE | 96.9 | 0 | 0 | 20
4 | HOOGHLY | Arambag | Electrical | Bhalia (Zone-II) Piped Water Supply Scheme, Block- Arambagh, District-Hooghly | SM/19014 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bhalia (Zone-II) water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/001983/2023-2024 | 115/ED | 15/01/2024 | 31/05/2025 | A.G. ENTERPRISE | 20.49 | 0 | 0 | 20
Total | [13 empty] | 125.95 | 0 | 0