## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED GOPALDAHA PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' | SM/19015 | New | GOPALDAHA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Block Arambagh, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000553/2023-2024 | 3182/HUG | 30/10/2023 | 27/04/2025 | AYUSH ENTERPRISE | 76.72 | 29.15 | 37.99 | 50
2 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED GOPALDAHA PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' | SM/19015 | New | Material Requisition To Resource Division |  |  | RTOR000396/2023-2024 | 3057/53/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 1.82 | 0 | 0 | 0
3 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED GOPALDAHA PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' | SM/19015 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gopaldaha water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001654/2023-2024 | 05/ED | 02/01/2024 | 01/04/2024 | M/S CHANDIMATA ELECTRICALS | 20.49 | 7.46 | 36.41 | 20
4 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED GOPALDAHA PIPED WATER SUPPLY SCHEME IN ARAMBAGH BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT' | SM/19015 | New | Quotation of New Service Connection for Gopaldaha w/s Scheme,PH No-I Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/19015) Application No-5004148688, Reference Id-503632547 |  |  | BILL/00414/2024-2025 | 100 | 06/05/2024 | 06/05/2024 | WBSEDCL | 12.59 | 0 | 0 | 0
Total | [13 empty] | 111.63 | 36.61 | 32.8