## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District | SM/19036 | Augmentation | Construction of 16.75 m X 12 m Pumphouse including plinth protection and surface drain at Pandua IBS-I site ofSurface Water Base Piped Water Supply Scheme Balagarh & Pandua Under Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000605/2023-2024 | 3347/HUG | 17/11/2023 | 15/05/2024 | MS PRADIP KUMAR PAL | 64.72 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District | SM/19036 | Augmentation | Construction of C.W.R. (Clear water Reservoir) of capacity 350 Cu.m / 77000 Gallons & allied Work at Pandua IBS-I site of Surface Water Base Piped Water Supply Scheme Balagarh & Pandua Under Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000607/2023-2024 | 3349/HUG | 17/11/2023 | 15/05/2024 | MS PRADIP KUMAR PAL | 37.76 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District | SM/19036 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000546/2023-2024 | 3059/23/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 638.35 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District | SM/19036 | Augmentation | ROAD RESTORATION PAYMENT TO PWD FOR G.T.ROAD TO SARAI LINK ROAD ROAD |  |  | BILL/00676/2024-2025 | BP-2024-25-501 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 3.96 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District | SM/19036 | Augmentation | link road from STKK to Borail |  |  | BILL/00682/2024-2025 | BP-2024-25-501 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 3.85 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District | SM/19036 | Augmentation | PAYMENT TO ROAD RESTORATION TO PWD PANDUA ROAD |  |  | BILL/00690/2024-2025 | BP-2024-25-501 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 7.96 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District | SM/19036 | Augmentation | PAYMENT TO ROAD RESTORATION TO PWD PANDUA KANTAI ROAD |  |  | BILL/00691/2024-2025 | BP-2024-25-501 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 3.18 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District | SM/19036 | Augmentation | Balagarh Inchura Road Restoration |  |  | BILL/00675/2024-2025 | BP-2024-25-501 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 16.53 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District | SM/19036 | Augmentation | jeerat feeder road STKK to Balagarh |  |  | BILL/00677/2024-2025 | BP-2024-25-501 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 1.05 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District | SM/19036 | Augmentation | Tamba Kamarpara Road Restoration |  |  | BILL/00687/2024-2025 | BP-2024-25-501 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 16.81 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District | SM/19036 | Augmentation | feeder road from STKK to Balagarh |  |  | BILL/00680/2024-2025 | BP-2024-25-501 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 6.58 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District | SM/19036 | Augmentation | Feeder road from STKK to Khamargachi |  |  | BILL/00688/2024-2025 | BP-2024-25-501 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 4.03 | 0 | 0 | 0
13 | HOOGHLY |  | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District | SM/19036 | Augmentation | Tamba Ilchoba Road Restoration |  |  | BILL/00685/2024-2025 | BP-2024-25-501 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 9.39 | 0 | 0 | 0
14 | HOOGHLY |  | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District | SM/19036 | Augmentation | PAYMENT TO ROAD RESTORATION TO PWD RAHIMPUR KALNA ROAD |  |  | BILL/00692/2024-2025 | BP-2024-25-501 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 7.15 | 0 | 0 | 0
15 | HOOGHLY |  | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District | SM/19036 | Augmentation | Pandua Kulti Road Restoration |  |  | BILL/00670/2024-2025 | BP-2024-25-501 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 19.73 | 0 | 0 | 0
16 | HOOGHLY |  | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District | SM/19036 | Augmentation | ROAD RESTORATION PAYMENT TO PWD FOR NAKSA DIGSUI INCHURA ROAD |  |  | BILL/00674/2024-2025 | BP-2024-25-501 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 24.45 | 0 | 0 | 0
17 | HOOGHLY |  | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District | SM/19036 | Augmentation | ROAD RESTORATION PAYMENT TO PWD FOR SINGUR UGLY ROAD |  |  | BILL/00678/2024-2025 | BP-2024-25-501 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 21.76 | 0 | 0 | 0
18 | HOOGHLY |  | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District | SM/19036 | Augmentation | Feeder road from STKK |  |  | BILL/00673/2024-2025 | BP-2024-25-501 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 10.3 | 0 | 0 | 0
19 | HOOGHLY |  | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District | SM/19036 | Augmentation | Feeder road from STKK to Sripur Bazar Road |  |  | BILL/00689/2024-2025 | BP-2024-25-501 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 4.27 | 0 | 0 | 0
20 | HOOGHLY |  | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District | SM/19036 | Augmentation | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Pandua Block in Hooghly District with three months trial run & subsequent O&M for one year.. | Assistant Engineer (Civil),Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000594/2023-2024 | 3309/HUG | 10/11/2023 | 01/01/2026 | ECO PROTECTIONENGINEERS PVT LTD. | 19490.9 | 3306.97 | 16.97 | 25
21 | HOOGHLY |  | Hooghly Division | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District | SM/19036 | Augmentation | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh Block in Hooghly District with three months trial run & subsequent O&M for one year. | Assistant Engineer (Civil),Assistant Engineer(HQ) | Hooghly Division Junior Engineer,Junior Engineer (Civill) | ORD/000595/2023-2024 | 3310/HUG | 10/11/2023 | 01/01/2026 | ECO PROTECTIONENGINEERS PVT LTD. | 11029.1 | 1717.6 | 15.57 | 35
22 | HOOGHLY |  | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic affected Balagarh and Pandua Block in Hooghly District | SM/19036 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery for Intermediate Pumping Station (IPS-I) to be installed at Boinchi Gram and Intermediate Pumping Station (IPS-2) to be installed at Damdama Gram under Balagarh-Pandua Surface Based Pipe Water Supply Scheme, in the Dist. of Hooghly under Electrical Division, P.H.E, Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000007/2025-2026 | 660/ED | 24/04/2025 | 24/05/2025 | M/S S.S. ENTERPRISE | 234.37 | 0 | 0 | 0
Total | [13 empty] | 31656.18 | 5024.58 | 15.87