## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | Support-WQMSP | Engagement of 3 personnel (Chemist / Bacteriologist / Lab Assistant) in Serampore Sub District Water Testing Laboratory II under Hooghly Division PHE Dte For a period of 9 Months | Assistant Engineer(HQ) |  | ORD/000524/2023-2024 | 1597/HUG | 01/06/2023 | 26/02/2024 | DAS ENTERPRISE (SAMIR DAS) | 6.99 | 3.21 | 45.86 | 80
2 | HOOGHLY |  | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | Support-WQMSP | PAYMENT OF NGO LAB FOR SALARY FOR THE MONTH OF JANUARY-24 & FEBRUARY-24 |  |  | BILL/01553/2023-2024 | BP-2023-24-885 | 06/03/2024 |  | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 1.03 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | Support-WQMSP | PAYMENT OF NGO LAB FOR SALARY FOR THE MONTH OF JANUARY-24 & FEBRUARY-24 |  |  | BILL/01554/2023-2024 | BP-2023-24-884 | 06/03/2024 |  | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 1.03 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | Support-WQMSP | PAYMENT OF NGO LAB FOR SALARY FOR THE MONTH OF JANUARY-24 & FEBRUARY-24 |  |  | BILL/01555/2023-2024 | BP-2023-24-883 | 06/03/2024 |  | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 1.03 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | Support-WQMSP | Engagement of 9 personnel (Chemist / Bacteriologist and One Lab-Assistant) in Kamrpukur, Serampore, Chandannagar and Jangipara each of 04 new water testing laboratories under Hooghly Division P.H.E. Dte. (From 01.02.2024 to 31.07.2024) 06 Months. | Assistant Engineer(HQ) |  | ORD/000982/2023-2024 | 514/HUG | 19/02/2024 | 17/08/2024 | PRADIP KUMAR ADHYA | 14.64 | 6.44 | 44.01 | 15
6 | HOOGHLY |  | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | Support-WQMSP | Engagement of 6 personnel (Sampling Assistant / Lab Attendant) in Water Testing Laboratories under Hooghly Division PHE Dte. (From 01.02.2024 to 31.12.2024) 11 Months. | Assistant Engineer(HQ) |  | ORD/000983/2023-2024 | 515/HUG | 19/02/2024 | 14/01/2025 | PRADIP KUMAR ADHYA | 7.66 | 4.61 | 60.2 | 15
7 | HOOGHLY |  | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | Support-WQMSP | PAYMENT OF NGO LAB FOR SALARY |  |  | BILL/00019/2024-2025 | null | 08/04/2024 |  | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.51 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | Support-WQMSP | PAYMENT OF NGO LAB FOR SALARY |  |  | BILL/00018/2024-2025 | null | 08/04/2024 |  | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.51 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | Support-WQMSP | PAYMENT OF NGO LAB FOR SALARY |  |  | BILL/00017/2024-2025 | null | 08/04/2024 |  | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.51 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | Support-WQMSP | Engagement of 3 personnel (Chemist / Bacteriologist / Lab Assistant) in Chandannagar Sub District Water Testing Laboratory II under Hooghly Division PHE Dte. | Assistant Engineer(HQ) |  | ORD/000019/2024-2025 | 1931/HUG | 07/05/2024 | 07/05/2025 | PRADIP KUMAR ADHYA | 7.22 | 1.96 | 27.15 | 0
11 | HOOGHLY |  | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | Support-WQMSP | PAYMENT TO NGO LAB FOR THE MONTH OF-APRIL-24 |  |  | BILL/00236/2024-2025 | BP-2024-25-160 | 22/05/2024 |  | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.51 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | Support-WQMSP | NGO LAB PAYMENT FOR THE MONTH OF APRIL-24 |  |  | BILL/00237/2024-2025 | BP-2024-25-158 | 22/05/2024 |  | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.51 | 0 | 0 | 0
13 | HOOGHLY |  | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | Support-WQMSP | NGO LAB PAYMENT FOR THE MONTH OF APRIL-24 |  |  | BILL/00238/2024-2025 | BP-2024-25-159 | 22/05/2024 |  | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.51 | 0 | 0 | 0
14 | HOOGHLY |  | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | Support-WQMSP | PAYMENT TO NGO LAB FOR THE MONTH OF MAY-2024 |  |  | BILL/00322/2024-2025 | BP-2024-25-240 | 02/07/2024 |  | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.51 | 0 | 0 | 0
15 | HOOGHLY |  | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | Support-WQMSP | PAYMENT FOR NGO LAB FOR THE MONTH OF MAY-2024 |  |  | BILL/00323/2024-2025 | BP-2024-25-241 | 02/07/2024 |  | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.51 | 0 | 0 | 0
16 | HOOGHLY |  | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | Support-WQMSP | PAYMENT FOR NGO LAB FOR THE MONTH OF MAY-2024 |  |  | BILL/00324/2024-2025 | BP-2024-25-239 | 02/07/2024 |  | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.51 | 0 | 0 | 0
17 | HOOGHLY |  | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | Support-WQMSP | PAYMENT TO NGO LAB FOR THE MONTH OF JUNE-24 |  |  | BILL/00389/2024-2025 | BP-2024-25-306 | 16/07/2024 |  | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.51 | 0 | 0 | 0
18 | HOOGHLY |  | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | Support-WQMSP | PAYMENT TO NGO LAB FOR THE MONTH OF JUNE-24 |  |  | BILL/00388/2024-2025 | BP-2024-25-304 | 16/07/2024 |  | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.51 | 0 | 0 | 0
19 | HOOGHLY |  | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | Support-WQMSP | PAYMENT TO NGO LAB FOR THE MONTH OF JUNE-24 |  |  | BILL/00390/2024-2025 | BP-2024-25-305 | 16/07/2024 |  | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.51 | 0 | 0 | 0
20 | HOOGHLY |  | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | Support-WQMSP | NGO LAB PAYMENT FOR THE MONTH OF JULY-24 |  |  | BILL/00487/2024-2025 | BP-2024-25-368 | 06/08/2024 |  | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.51 | 0 | 0 | 0
21 | HOOGHLY |  | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | Support-WQMSP | Salary for the Staff For the month of August 2024 |  |  | BILL/00569/2024-2025 | null | 06/09/2024 |  | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.51 | 0 | 0 | 0
22 | HOOGHLY |  | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | Support-WQMSP | NGO LAB PAYMENT FOR THE MONTH OF JULY-24 |  |  | BILL/00488/2024-2025 | BP-2024-25-367 | 06/08/2024 |  | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.51 | 0 | 0 | 0
23 | HOOGHLY |  | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | Support-WQMSP | Salary for the Staff For the month of August 2024 |  |  | BILL/00567/2024-2025 | null | 06/09/2024 |  | SARVIK VIVEKANANDA GRAM SEVA SANSTHA | 0.51 | 0 | 0 | 0
24 | HOOGHLY |  | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | Support-WQMSP | Salary for the Staff For the month of August 2024 |  |  | BILL/00568/2024-2025 | null | 06/09/2024 |  | NETAJI MAHAVIDYALAYA WATER TESTING LAB | 0.51 | 0 | 0 | 0
25 | HOOGHLY |  | Hooghly Division | Operational charges for 09 (Nine) nos. NABL Accridited/Recognised PHED & NGO Managed Laboratories under Hooghly Division, PHE Dte | SM/19085 | Support-WQMSP | NGO LAB PAYMENT FOR THE MONTH OF JULY-24 |  |  | BILL/00489/2024-2025 | BP-2024-25-366 | 06/08/2024 |  | AMARTYA RURAL WELFARE & RESEARCH CENTRE | 0.51 | 0 | 0 | 0
Total | [13 empty] | 48.81 | 16.22 | 33.24